## Info & Expectations
* Reference deliverables required for each level of estimate grade
Table of Deliverables for Estimates by Estimate Grade |  |  |  |  | 2023-04-04 | Rev 01
Level of estimate | Order of Magnitude (OOM) | Conceptual | Planning | Detailed | IFC | Partial Funding
| SDC ( alternates) | SDC (preferred alt) | Full Funding |  |  | Not Distinct Est. Category
| -50% / 200% | -25% / 50% | -25% / 25% | -10% / 10% | -10% / 10%
Engr. Deliverables by discipline with project scope | OOM | Conceptual | Preliminary | Detailed | IFC
Engr. Deliverables Checklist by each disipline with project scope | OOM | Conceptual | Preliminary | Detailed | IFC
P6 Schedule | NA | NA | Required | Required | Required
Milestone dates | Required | Required |  |  |  | Required
Construciblilty review (Form) | NA | Overview - constr. execution | Detailed | Detailed | Detailed
Input (scope & cost) from supporting groups
Siting | NA | Type of Siting Req'd | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Project services | NA | Type of Outreach Req'd | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Enviromental | NA | Any major costs anticipated such as a large remediation effort | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Legal |  |  | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Land | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Vendor or Const. bids |  | Any Available | Any Available | Any Available | Any Available | Any Available
Actuals to date (Formatted by E-Builder WBS codes) |  | Required | Required | Required | Required | Required
Risks Identification
Single Contingency Line Loss | Identify Potential | Identify Potential | Required | Required | Required
ERM impacts ( if applicable) | Identify Potential | Identify Potential | Required | Required | Required

## Estimate Basis
Review Status
ESTIMATE BASIS |  |  |  | Stage | Complete | Status | Reviewer
| Project Title: |  | Estimate #: | Peer 1 | YES | Review Completed | A. Bevilacqua
| Project Mgr/Lead: |  | Date of Estimate: | Peer 2 | YES | Review Completed | littlefield
| Project Number: |  | Estimate done by: | Lead 1 | NO | _
| WO & Task #: |  | In Service date (ISD): | Lead 2 | N/A | _
|  |  |  | MGMT | NO | _
Estimate Scope
EPAC notes
Project unit costs
Cost drivers
Estimate Conditions
Scoping Documents
| Date | Name | Location

## Peer Review
Estimate Review Comments Tracking
Peer Review
Reviewer | Item # | Item /Tab |  | Review Comments |  | Estimator reply | Other Notes
Reviewer #1
A. Bevilacqua |  | Review Completed |  |  | 2026-01-23
| 1 | Nav | Should we be utilizing the 'N/A' option for estimating accuracy grade instead of planning for PF? |  |  | Checked.
| 2 | Scope | The PF request direct cost listed in the scope ($4.009M) appears to be the prior authorized amount not the ask. |  |  | Checked.
| 3 | Schedule | Project team doesn't foresee anymore Project Management support for the remaining of the year before FF? CRs? |  |  | Checked.
| 4 | Materials | Use of LNTP or MOER from PT for the material costs since they are greater than what we carry for Partials? |  |  | Checked.
| 5 | PAF | Reminder to hide year 2030 on your PAF. |  |  | Checked.
6
7
8
9
10
Reviewer #2
littlefield |  | Review Completed |  |  | 2025-01-23
| 1 | ESF | ISD date? |  |  | checked
| 2 | PF Template | PMT burn rate to date $700k; agree w/Ava, more to come |  |  | checked
| 3 |  | Data incomplete - lacks prior authorized, to complete picture |  |  | checked
4
5
6
7
8
9
10
Recommendations
-
-
-
-
-
-
-
-
-
-

## Lead Review
Lead Review
Review Req'd By | Item # | Item /Tab | Review Comments | Estimator reply | Other Notes
_
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
_
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Managerial Review
Managerial Review
Review Req'd By | Item # | Item /Tab | Review Comments | Estimator reply | Other Notes
Ghari Bassaragh |  | _
1
2
3
4
5
6
7
8
9
10

## Estimate Closeout
Estimate Closeout Checklist (complete before submission of estimate to requester)
Item |  | Complete | Notes
Pre-Submission Checklist
Peer Reviews complete
Lead Review complete
ESF Created and verified
All scoping information included in ESF
Archive
Estimate Request
Scope Basis Information
General Email Correspondence
Submitted ESF in Estimate folder
Pertinent Information Uploaded to Database
Estimate Log Updated
Date Scoping Received Filled Out
Self-Check Completed
Basis Checklist Completed
Summary and Assumptions Documented
Cover, PAF and Detail Sum Totals Match
Costs in-line with Benchmark? If not address on cover.
Review Completed |  |  | See estimate review comments tab