# ATTACHMENT

# EPAC MATERIAL ORDER EXCEPTION PROCESS REQUEST FORM for Authorization

Owners:

Paul Melzen

Director, Substation Design – Substation Design Leadership

Helen M. Taylor

Project Solutions Manager

DATE: July 2025

Note: This is an attachment to the Material Order Exception Form Process

Material Order Exception Request Form

(Material Orders Requested Prior to Preliminary Design/Full Funding)

| Date Prepared: 01/15/2026 | Project Title: Hyde Park BESS |
| --- | --- |
| Company/ies: Eversource EMA | Project ID Number: 21334 |
| Managing Organization: Project Mgt and Construction | Class of Plant: D SS |
| Exception Requestor: Adam Kelley | Project Category: Stations - General |
| Project Initiator: Amsa Mangga Project Manager: Adam Kelley | Est. Construction Start Date: 08/31/2027 Est. In Service Date: 08/28/2028 |
| Total Request: $1,210,685 Total Equipment Cost: $12,106,850 | SSF approved? Yes Current Funding Status: $4,009,000 Partial Funding Requesting: $1,510,685 (Feb 2026) Equipment delivery date: 11/26/2027 |
| Project Solutions Management Review: yes | All requested materials stock coded in Maximo? No |

Justification for Material Order Prior to Full Funding (Include Funding and Engineering Status to date):

The Hyde Park Substation peak load for year 2025 exceeded the station firm capacity and incrementally keeps increasing. From 2021 through 2024, there have been multiple transfers to keep the peak load on the station within the firm capacity. Even with these load transfers, the Hyde Park Substation peak load exceeded the station firm capacity 2025. Continued load transfers are not a feasible option because they reduce the existing circuit transfer capability, increase the existing distribution lines’ exposure, and reducing the spare capacity at the receiving Substations. Any further transfers can only be done temporarily and are not a viable long-term solution. Once emergency transfers are exhausted, the Company will need to resort to other measures, such as the use of spot generation to pick up any additional remaining load. The BESS is needed to provide additional firm capacity at STA 496 (Hyde Park) until construction is complete and load can be transferred to STA 494 (New England Ave).

The Project team is requesting approval of this Material Order Exemption Request to issue a Purchase Order (PO) with a Limited Notice to Proceed (LNTP) with NOMAD Power Solutions for the Battery Energy Storage System (BESS). This is required in order to secure a manufacturing slot and receive engineering drawings and data so that balance of plant equipment can be ordered, and the preliminary engineering design package can be completed.

The Hyde Park BESS project is scheduled to receive full funding in Q4 2026. Long Lead material must be received onsite in Q4 2027

To meet the lead time requirements for the current ISD, the project team must issue Purchase Orders (PO’s) with a Limited Notice to Proceed (LNTP), well ahead of Full Funding approval.

- BESS Battery System

The project team requests authorization of this material order exception request form to secure the Battery portion of the BESS through the timely issuance of the Purchase Orders in order to keep the current project ISD of August 2028.

| High Level Milestones​​ | HYDE PARK BESS |
| --- | --- |
| Work Order # | 80089926 |
| Preliminary Design Complete | Sep 2026 |
| Detailed Design Complete​​ | Apr 2027 |
| Full Funding EPAC​​ | Dec 2026 |
| IFC Design Complete | May 2027 |
| Start of Construction | Aug 2027 |
| Planned Material On-Site | Nov 2027 |
| In-Service Date​​ | Aug 2028 |

The P6 Schedule has been developed under Work Order# 80089926 and is in Active status for reporting.

Plan to Fund Material Order:

Partial funding requests are August 14, 2023 (Rev 0), February 15, 2024 (Rev 1), and February 27, 2025 (Rev 2).

Partial funding amount of $1,510,685 for Feb 5, 2026 EPAC.

A revised partial funding request for Hyde Park BESS project with an updated authorized budget of $5,519,685K was submitted to EPAC for the February agenda.

The following material will need to be ordered prior to full funding to meet the current in-service date due to material lead times, which are 15 months after receipt of order, and drawing lead times, which are 12-16 weeks after receipt of order. Drawings are required to complete preliminary design deliverables for EPAC.

- Battery Energy Storage System

  - DC Power Blocks and Tier 1 controls with required HVAC and Fire protection

The following is a list for the Hyde Park BESS System payment comment for pre and post full funding.

Milestone Payment Commitments Prior to Full funding:

- Battery Energy Storage System

  - 10% Payment ($1,210,685) to support drawing development and reserve manufacturing slot.

Milestone Payment Commitments After Full Funding:

- Battery Energy Storage System

  - 40% Payment for delivery.

This project is expecting Siting Approval in Q4 2027. There are no other projects currently on the books that could utilize the equipment covered by this MOER.

Equipment Summary:

| Material Details |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Equipment Type | Vendor Quote (Yes/No) | Description | Lead Time (Weeks) | Total Cost ($) | Payment before Full Funding % | Funding Request ($) |
| Batteries (Package #1) | Yes | Batteries, Racks, Disconnects, Inverters, Control System, Fire Suppression Equipment & Generator Step-Up Transformer | 60 | $12,106,850 | 10% | $1,210,685 |
|  |  |  |  | Total |  | $1,210,685 |

Payment Timing Summary:

| Material Payment Commitments BEFORE Full Funding |  |  |  |  |
| --- | --- | --- | --- | --- |
| Equipment | Milestone Description | Payment Amount | Expected Date |  |  |
| Batteries (Package #1) | Submittal of Preliminary Project Schedule – 5% | $605,342 | 5/15/26 |  |  |
|  | Final Drawings: Design Drawings reviewed and finalized, and Shop Drawings Approved – 5% | $605,342 | 7/13/26 |  |  |
|  | Total | $1,210,685 |  |  |  |

| Material Payment Commitments AFTER Full Funding |  |  |  |  |
| --- | --- | --- | --- | --- |
| Equipment |  | Milestone Description | Payment Amount | Expected Date |
| Batteries (Package #1) |  | Factory Acceptance Testing (FAT) (at the last piece of equipment) – 35% | $4,237,397 | 11/26/27 |
|  |  | Material Delivery (at the last piece of equipment) – 40% | $4,842,740 | 1/28/28 |
|  |  | Final Acceptance – 15% | $1,816,027 | 8/14/28 |
|  |  | Total | $10,896,164 |  |

Approving Signees:

Date______________________		Date______________________

Date______________________		Date______________________

Date______________________