## Info & Expectations
* Reference deliverables required for each level of estimate grade
Table of Deliverables for Estimates by Estimate Grade |  |  |  |  | 2023-04-04 | Rev 01
Level of estimate | Order of Magnitude (OOM) | Conceptual | Planning | Detailed | IFC | Partial Funding
| SDC ( alternates) | SDC (preferred alt) | Full Funding |  |  | Not Distinct Est. Category
| -50% / 200% | -25% / 50% | -25% / 25% | -10% / 10% | -10% / 10%
Engr. Deliverables by discipline with project scope | OOM | Conceptual | Preliminary | Detailed | IFC
Engr. Deliverables Checklist by each disipline with project scope | OOM | Conceptual | Preliminary | Detailed | IFC
P6 Schedule | NA | NA | Required | Required | Required
Milestone dates | Required | Required |  |  |  | Required
Construciblilty review (Form) | NA | Overview - constr. execution | Detailed | Detailed | Detailed
Input (scope & cost) from supporting groups
Siting | NA | Type of Siting Req'd | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Project services | NA | Type of Outreach Req'd | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Enviromental | NA | Any major costs anticipated such as a large remediation effort | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Legal |  |  | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Land | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Vendor or Const. bids |  | Any Available | Any Available | Any Available | Any Available | Any Available
Actuals to date (Formatted by E-Builder WBS codes) |  | Required | Required | Required | Required | Required
Risks Identification
Single Contingency Line Loss | Identify Potential | Identify Potential | Required | Required | Required
ERM impacts ( if applicable) | Identify Potential | Identify Potential | Required | Required | Required

## Estimate Basis
Review Status
ESTIMATE BASIS |  |  |  |  | Stage | Complete | Status | Reviewer
| Project Title: | Hyde Park BESS - PF 3 | Estimate #: |  | Peer 1 | YES | Review Completed | S. Martin
| Project Mgr/Lead: | Adam Kelly | Date of Estimate: | 2026-06-10 | Peer 2 | NO | 0
| Project Number: | 21334 | Estimate done by: | Brian Roche | Lead 1 | YES | Estimate Approved | Justin Niderno
| WO & Task #: | 80089926 | In Service date (ISD): | 2026-12-31 | Lead 2 | N/A | _
[5 empty] | MGMT | NO | _
Estimate Scope
EPAC notes
Project unit costs
[5 empty] | Cost drivers | All costs provided by the project manager.
Estimate Conditions
Scoping Documents
| Date | Name | Location
This revised partial funding Project Authorization Form (PAF) is a request for an
additional $11.5M for completion of preliminary engineering, a Limited Notice to Proceed (LNTP) and 10% down for procurement of engineering drawings for the Battery System, project management, siting, environmental and project services support and preparation of a full funding PAF package.
This project is to construct a 10MW/20MWh Battery Energy Storage System (BESS) at 401-433
Cummins Highway (future Hyde Park BESS Station #359) in the Hyde Park section of the City of
Boston to help relieve the heavy loading condition of Hyde Park Substation #496 in Hyde Park,
MA.
Actual start date: 7/2021
Actuals to 6/3/26, $3,828,338.
EPAC ful funding date: 11/30/26.
ISD date: 12/28/2028.

## Peer Review
Estimate Review Comments Tracking
Peer Review
Reviewer | Item # | Item /Tab |  | Review Comments |  | Estimator reply | Other Notes
Reviewer #1
S. Martin |  | Review Completed |  |  | 2026-06-10
| 1 | Cover | Suggested rewording of project scope on cover tab : This revised partial funding Project Authorization Form (PAF) is a request for $11.5 M for completion of preliminary engineering, a Limited Notice to Proceed (LNTP) and 10% down for procurement of engineering drawings for the Battery System, project management, siting, environmental and project services support and preparation of a full funding PAF package. |  |  | Complete 6/10/26
| 2 | Sage | To avoid confusion (as it shows up as environmental) maybe put $100K of legal requested under PM line item not " Legal, Environmental, Contractor" as it may not be related to environmental activities |  |  | Complete 6/10/26
3
D. Piccorelli |  | Review Completed |  |  | 2026-06-10
| 5 | Project Level | Scope - check spelling |  |  | Complete 6/10/26
| 6 | Clarifications | Add note where the costs came from. |  |  | Complete 6/10/26
7
8
9
10
2
3
4
5
6
7
8
9
10
Recommendations
-
-
-
-
-
-
-
-
-
-

## Lead Review
Lead Review
Review Req'd By | Item # | Item /Tab | Review Comments | Estimator reply | Other Notes
Justin Niderno |  | Estimate Approved | 2026-06-12
1
| 2 |  | Several questions for PM answered - good to go | Complete 6/12/26
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
_
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Managerial Review
Managerial Review
Review Req'd By | Item # | Item /Tab | Review Comments | Estimator reply | Other Notes
Ghari Bassaragh |  | _
1
2
3
4
5
6
7
8
9
10

## Estimate Closeout
Estimate Closeout Checklist (complete before submission of estimate to requester)
Item |  | Complete | Notes
Pre-Submission Checklist
Peer Reviews complete
Lead Review complete
ESF Created and verified
All scoping information included in ESF
Archive
Estimate Request
Scope Basis Information
General Email Correspondence
Submitted ESF in Estimate folder
Pertinent Information Uploaded to Database
Estimate Log Updated
Date Scoping Received Filled Out
Self-Check Completed
Basis Checklist Completed
Summary and Assumptions Documented
Cover, PAF and Detail Sum Totals Match
Costs in-line with Benchmark? If not address on cover.
Review Completed |  |  | See estimate review comments tab