## Sheet1
Hyde Park BESS - 21334 - Partial Funding | Our next Partial Funding needs to be presented to EPAC on Jun 25 and not July and needs to encompass remaining long lead material, engineering, SSP, siting and permitting.
Item | Breakdown / Payment / Notes | Vendor | Costs | POC to verify | Verified? | 1 | 2 | PF | Column1
Milestone Payment - LNTP | Submittal of Preliminary Project Schedule - Final Drawings: | Nomad | 0 | Payment Milestone Schedule |  |  |  | Rev 2 | Funded
Milestone Payment - LNTP | Design Drawings reviewed and finalized, and Shop Drawings Approved | Nomad | 0 | Payment Milestone Schedule |  |  |  | Rev 2 | Funded
Milestone Payment - FNTP (External) | Upon Issuance of Final Notice to Proceed | Nomad | 1210685 | Payment Milestone Schedule | Yes | Milestone Payment Expected 7/28/26 |  | Rev 3 | Payment prior to FF
Long lead material (LLM) costs (External) | Metal Clad Switchgear | RFP | 1000000 | PM/Engineering | Yes | Identify % for PF vs FF 20% for PF Rev 3 ($1M) 80% for FF ($4M) | What is the updated Switchgear pricing after revisions? ($5,000,000 per Patrick) | Rev 3 | 20% payment
| GSU Battery Transformers (4x500k) | RFP | 400000 | PM/Engineering | Yes | Identify % for PF vs FF 20% for PF Rev 3 ($400K) 80% for FF ($1.6M) | Nomad provided information will lead Engineering to create spec and pricing for GSU, pending PSCAD Model. (4x500k=$2,000,000 per Patrick) | Rev 3 | 20% payment
Engineering costs up to IFC (External) | Engineering work to be completed by external vendors: | Leidos | 1500000 | John Z/Rosa | Yes | (IFC Complete 8/2027) | Requested value from Engineering - Vendor proposal received 5/29 ($1.5M proposal - full amount needed to complete majority of work for Sep/Oct 2026 to meet Siting filing deadline - ultimately ahead of FF in Nov/Dec 2026) | Rev 3
| Engineering work to be completed by external vendors: | VHB | 59300 | John Z/Rosa | Yes | (IFC Complete 8/2027) | Vendor Proposal received | Rev 3
Engineering costs up to IFC (Internal) | Internal Engineering hours for Station Design, Communications Engineering, P&C Engineering, Substation Technical Engineering and Capital Projects |  | 402062 | John Z/Rosa | Yes | (IFC Complete 8/2027) | Requested value from Engineering - 6433 hours | Rev 3
SSP T&M Costs (External) | The scope of this RFP includes early contractor engagement: assistance with the development of Engineering & Siting Deliverables, Detailed Project Estimates, Constructability Reviews, Design reviews, Preliminary Schedule, along with the execution of both standard and BESS specific system components to meet the December 2028 in-service date.​ | Haugland | 607582.7 | Vendor proposal | Yes | Identify PF LNTP ($269,395.85) PF (Balance w/contigency) ($338,186.85) | ($553,791.70 + $53,791.00 contingency) = $607,582.70 Phase 1 (Preliminary Part A) - $269,395.85 - LNTP Phase 1 (Detailed Part B) - $269,395.85 - PF | Rev 3
PM/Scheduler Costs up to FF (PM Support Team) (Internal) | *Cost shown is w/o actuals |  | 248000 | Kasia | Yes | (EPAC Approval for Full Funding 11/2026) |  | Rev 3
Continued Siting and Permitting up to FF (Internal) | *Cost shown is w/o actuals |  | 25000 | Kasia | Yes | (EPAC Approval for Full Funding 11/2026) |  | Rev 3
Siting Legal Costs up to FF (External) | Work to be completed by external vendor for Legal Services (KW) |  | 100000 |  | Yes | (EPAC Approval for Full Funding 11/2026) | Trending to 75-100k through Dec 2026 | Rev 3
Milestone Payment - FNTP | Equipment FAT (at the last piece of equipment) | Nomad | 0 | Payment Milestone Schedule | Yes | Milestone Payment Expected 11/26/27 | Remove from PF Rev 3 - Add to Full Funding ($3,632,055.00) | FF | Payment after FF
Milestone Payment - FNTP | Equipment Delivery to Site (at the last piece of equipment) | Nomad | 0 | Payment Milestone Schedule | Yes | Milestone Payment Expected 1/28/28 | Remove from PF Rev 3 - Add to Full Funding ($4,842,740.00) | FF | Payment after FF
Milestone Payment - FNTP | Final Acceptance | Nomad | 0 | Payment Milestone Schedule | Yes | Milestone Payment Expected 8/14/28 | Remove from PF Rev 3 - Add to Full Funding ($1,210,685.00) | FF | Payment after FF
Long lead material (LLM) costs | Switchgear | RFP | 0 | PM/Engineering | Yes | Identify % for PF vs FF 20% for PF Rev 3 ($1M) 80% for FF ($4M) | What is the updated Switchgear pricing after revisions? ($5,000,000) | FF
| GSU (4x500k) |  | 0 | PM/Engineering | Yes | Identify % for PF vs FF 20% for PF Rev 3 ($400K) 80% for FF ($1.6M) | Nomad provided information will lead Engineering to create spec and pricing for GSU, pending PSCAD Model. ($2,000,000 per Patrick) | FF
5552629.7
$5,552,629.70 (Rev 3 Partial Funding Request) + $3,828,337 (Actuals given by Sean - Actuals only) = $9,380,967