## Info & Expectations
* Reference deliverables required for each level of estimate grade
Table of Deliverables for Estimates by Estimate Grade |  |  |  |  | 2023-04-04 | Rev 01
Level of estimate | Order of Magnitude (OOM) | Conceptual | Planning | Detailed | IFC | Partial Funding
| SDC ( alternates) | SDC (preferred alt) | Full Funding |  |  | Not Distinct Est. Category
| -50% / 200% | -25% / 50% | -25% / 25% | -10% / 10% | -10% / 10%
Engr. Deliverables by discipline with project scope | OOM | Conceptual | Preliminary | Detailed | IFC
Engr. Deliverables Checklist by each disipline with project scope | OOM | Conceptual | Preliminary | Detailed | IFC
P6 Schedule | NA | NA | Required | Required | Required
Milestone dates | Required | Required |  |  |  | Required
Construciblilty review (Form) | NA | Overview - constr. execution | Detailed | Detailed | Detailed
Input (scope & cost) from supporting groups
Siting | NA | Type of Siting Req'd | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Project services | NA | Type of Outreach Req'd | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Enviromental | NA | Any major costs anticipated such as a large remediation effort | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Legal |  |  | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Land | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost | Scope & Cost
Vendor or Const. bids |  | Any Available | Any Available | Any Available | Any Available | Any Available
Actuals to date (Formatted by E-Builder WBS codes) |  | Required | Required | Required | Required | Required
Risks Identification
Single Contingency Line Loss | Identify Potential | Identify Potential | Required | Required | Required
ERM impacts ( if applicable) | Identify Potential | Identify Potential | Required | Required | Required

## Estimate Basis
Review Status
ESTIMATE BASIS |  |  |  |  | Stage | Complete | Status | Reviewer
| Project Title: | Hyde Park BESS | Estimate #: |  | Peer 1 | YES | Review Completed | PAG
| Project Mgr/Lead: | Robert Herman | Date of Estimate: | 2026-08-24 | Peer 2 | YES | Review Completed | D. Piccorelli
| Project Number: | 21334 | Estimate done by: | Brian Roche | Lead 1 | YES | Conditional approval | Justin Niderno
| WO & Task #: | 80089926 | In Service date (ISD): | 12/28/285 | Lead 2 | N/A | _
[5 empty] | MGMT | NO | _
Estimate Scope
EPAC notes
Project unit costs
[5 empty] | Cost drivers | 200'x200' - Develop a New SS Site.
Twelve (12) - Normad Voyager Eagle LFP BESS Systems with 251"x108" Foundation Pads.
Four (4) - 15 kV, Siemens SDV7 Standalone, 1,200-Amps Breaker with Foundations.
(2.5 Acres) - Clear and Grub.
(1.75 Acres) - Clear Wooded Area for Access Road.
Estimate Conditions
Scoping Documents
| Date | Name | Location
Installation of a 10MW/20MWH utility scale battery storage system (BESS) at 401-403 Cummings Highway near Hyde Park Substation #496 in Hyde Park, Boston MA.
Substation Design to integrate the existing 13.8 kV distribution infrastructure with a new Battery Energy Storage System (BESS) facility. Station 360 will include 4 standalone interconnection breakers, and the BESS system.
Site is a former landfill for construction debris and efforts will be made during the design process to limit excavation when possible.
No site conditions poise any challenges for the ground grid.
Soil borings are planned.
Eversource is the owner of the property.
Building construction is not required.
Per project team:
No control house
Breakers, $300k each, include skid, relays, PTs, hook type disconnect switches, DC battery,

## Peer Review
Estimate Review Comments Tracking
Peer Review
Reviewer | Item # | Item /Tab |  | Review Comments |  | Estimator reply | Other Notes
Reviewer #1
PAG |  | Review Completed | Hyde Park BESS - new station 360 |  | 2026-08-21
| 1 | Sage | bump your environmental Contractor hours to at least 160 beacause of the landfill |  |  | 40hrs to 160hrs both Eversource and Contractor - complete 8/24/26
| 2 | Sage | Increase your outreach hours because the area residents are not happy about this and were using eversource property for gardens and such. |  |  | 240 hrs to 480 mhrs Eversource and 40 hrs to 480 mhrs Contractor - complete 8/24/26
3
Reviewer #2
D. Piccorelli |  | Review Completed | Hyde Park BESS - new station 360 |  | 2026-08-24
| 1 | SAGE | Permits costs. |  |  | Complete 8/24/26
| 2 | SAGE | Include soil disposal |  |  | Complete 8/24/26
3
| 4 | SAGE | Risk, include cost for soil contamination |  |  | Complete 8/24/26
5
| 6 |  | Hyde Park BESS - new station 496 |  | 2026-08-24
| 7 | Estimate level | Key quantities |  |  | Complete 8/24/26
| 8 | ESF | Cont. 15% R/C |  |  | Complete 8/24/26
9
10
Recommendations
-
-
-
-
-
-
-
-
-
-

## Lead Review
Lead Review
Review Req'd By | Item # | Item /Tab | Review Comments | Estimator reply | Other Notes
Justin Niderno |  | Conditional approval
| 1 |  | Need CWIP set to yes | complete 8/25/26
2
| 3 |  | Suggest staying between 15-18% for Risk/contingency. | complete 8/25/26
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
_
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Managerial Review
Managerial Review
Review Req'd By | Item # | Item /Tab | Review Comments | Estimator reply | Other Notes
Ghari Bassaragh |  | _
1
2
3
4
5
6
7
8
9
10

## Estimate Closeout
Estimate Closeout Checklist (complete before submission of estimate to requester)
Item |  | Complete | Notes
Pre-Submission Checklist
Peer Reviews complete
Lead Review complete
ESF Created and verified
All scoping information included in ESF
Archive
Estimate Request
Scope Basis Information
General Email Correspondence
Submitted ESF in Estimate folder
Pertinent Information Uploaded to Database
Estimate Log Updated
Date Scoping Received Filled Out
Self-Check Completed
Basis Checklist Completed
Summary and Assumptions Documented
Cover, PAF and Detail Sum Totals Match
Costs in-line with Benchmark? If not address on cover.
Review Completed |  |  | See estimate review comments tab