## Cover
| E S T I M A T E S U M M A R Y | [15 empty] | Alt Estimate Summary for PP4 Calc ( escalation separate)
| Project Title: Battery Storage - Hyde Park | [7 empty] | Estimate #: E-23-373 | [7 empty] | Estimate #: E-23-373
| Project Mgr/Lead: Michael Rosenburg | [7 empty] | Date of Estimate:12/08/2023 | [7 empty] | Date of Estimate:12/08/2023
| Project Number: 21334 | [7 empty] | Estimate done by: PAG
| WO & Task #: 80089926 | [7 empty] | In Service date (ISD):04/23/2027
| Estimate revision #: 00 | [15 empty] | Project Number: 21334
| Estimate Type - Station work | [15 empty] | WO & Task #: 80089926
Template Revision # 01.92a
ESTIMATE SUMMARY
Estimate Type: Conceptual
WBS | Description | TOTAL | % of Directs | % of Total | Priors | 2024-01-01 | 2025-01-01 | 2026-01-01 |  | 2027-01-01 | 2028-01-01 | 2029-01-01 | 2030-01-01 | 2031-01-01 | 2032-01-01 | 2033-01-01 |  | TOTAL w/ escal broken out
1 | ROW / Easements / Land purchases | 0 | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROW / Easements / Land purchases | 0
2 | Environmental Approvals / Permits | 310100 | 1.058% | 0.706% | 5100 | 9200 | 74700 | 102600 |  | 118500 | 0 | 0 | 0 | 0 | 0 | 0 | Environmental Approvals / Permits | 284700
3 | Outreach | 275400 | 0.94% | 0.627% | 11000 | 0 | 46800 | 63000 |  | 123900 | 30700 | 0 | 0 | 0 | 0 | 0 | Outreach | 250000
4 | Siting Approvals / Permits | 252500 | 0.8619% | 0.5748% | 10300 | 0 | 42600 | 57800 |  | 113600 | 28200 | 0 | 0 | 0 | 0 | 0 | Siting Approvals / Permits | 229100
5 | Engineering / Design | 789600 | 2.695% | 1.798% | 16400 | 0 | 330700 | 390200 |  | 17400 | 34900 | 0 | 0 | 0 | 0 | 0 | Engineering / Design | 734400
6 | Materials ( Eversource purchased) | 13761800 | 46.97% | 31.33% | 2400 | 0 | 4449400 | 4678400 |  | 4631600 | 0 | 0 | 0 | 0 | 0 | 0 | Materials ( Eversource purchased) | 13098800 | move contractor mat'l to mat'l
7 | Construction ( incl materials by contractors) | 6921200 | 23.62% | 15.76% | 11000 | 0 | 500 | 500 |  | 5136500 | 1772700 | 0 | 0 | 0 | 0 | 0 | Construction ( incl materials by contractors) | 6107500 | 1500
8 | Testing / Commissioning | 1063800 | 3.631% | 2.422% | 0 | 0 | 0 | 0 |  | 311500 | 752300 | 0 | 0 | 0 | 0 | 0 | Testing / Commissioning | 926400
9 | PMT Project Mgmt Team | 1037700 | 3.542% | 2.362% | 74300 | 8400 | 36500 | 133600 |  | 404200 | 380700 | 0 | 0 | 0 | 0 | 0 | PMT Project Mgmt Team | 927800
10 | Removals | 0 | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Removals | 0
11 | Other ( property taxes and BAR) | 934900 | 3.191% | 2.128% | 6500 | 4200 | 102800 | 260000 |  | 561400 | 0 | 0 | 0 | 0 | 0 | 0 | Other ( property taxes and BAR) | 845500
12 | Risks | 3950000 | 13.48% | 8.992% | 0 | 0 | 0 | 900000 |  | 1650000 | 1400000 | 0 | 0 | 0 | 0 | 0 | Risks | 3950000
125 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Directs Total w/Risks | 29297000 | 100% | 66.7% | 137000 | 21800 | 5084000 | 6586100 |  | 13068600 | 4399500 | 0 | 0 | 0 | 0 | 0 |  | 27354200
13 | Indirects/Overhead | 9522600 |  | 21.68% | 209100 | 40400 | 754400 | 956600 |  | 5181500 | 2380600 | 0 | 0 | 0 | 0 | 0 | Indirects/Overhead | 8505600
14 | AFUDC | 3298600 |  | 7.509% | 25400 | 2800 | 228100 | 723900 |  | 1660900 | 657500 | 0 | 0 | 0 | 0 | 0 | AFUDC | 3298600
125 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Project Total - Baseline Budget | 42118200 |  | 95.88% | 371500 | 65000 | 6066500 | 8266600 |  | 19911000 | 7437600 | 0 | 0 | 0 | 0 | 0 |  | 39158400
0
15 | Contingency | 1807900 |  | 4.116% | 0 | 1000 | 458000 | 482000 |  | 748000 | 118900 | 0 | 0 | 0 | 0 | 0 | Contingency | 1807900
125 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Total - Funding Approval Level | 43926100 |  | 100% | 371500 | 66000 | 6524500 | 8748600 |  | 20659000 | 7556500 | 0 | 0 | 0 | 0 | 0 |  | 40966300
0
16 | Reimbursables/Customer Contribution | 0 |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
125 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
125 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Project Total (less reimbursables) | 43926100 |  |  | 371500 | 66000 | 6524500 | 8748600 |  | 20659000 | 7556500 | 0 | 0 | 0 | 0 | 0 |  | 40966300
| Cost per key qty (if appl) | 43926100 | $'s / LS BESS
| Amount of Escalation included above | 2960200 |  |  | 0 | 0 | 196200 | 390800 |  | 1637100 | 736100 | 0 | 0 | 0 | 0 | 0 |  | 2960200
6 | Total materials - Eversource | 13761800 |  |  | 2400 | 0 | 4449400 | 4678400 |  | 4631600 | 0 | 0 | 0 | 0 | 0 | 0
| Total materials - Contractor | 33458 |  |  | -42 | 0 | 500 | 500 |  | 24300 | 8200 | 0 | 0 | 0 | 0 | 0 | Escal total | 43926500
| Total materials | 13795258 |  |  | 2358 | 0 | 4449900 | 4678900 |  | 4655900 | 8200 | 0 | 0 | 0 | 0 | 0 | Check total | 400
NOTE: Risk / Contingency is 15.1% of Project Total Costs (incl escal/indirects/AFUDC but excl reimb.)
| Estimate Range | -25% |  | - | 50%
|  | 32945000 |  | - | 65889000
COMMENTS:
Project Scope: Battery Energy Storage System
| Key qty's and UOM ( tie to inputs on est sheets) | 1 | LS | BESS |  | 3.1919 | Factor ( total $/Eversource Mat'l $'s)
[6 empty] | 2.1289 | Factor ( Total directs $/Total Eversource mat'l $'s)
Assumptions/Clarifications;
| Indirect rates based on; | 21D - EMA , Station work
RISKS
| Potential UG Obstructions |  |  |  | 350000 |  | 0
| Severe Weather, Delays, OT |  |  |  | 900000 |  | 0
| Design development |  |  |  | 500000 |  | 0
| Additional outreach |  |  |  | 700000 |  | 0
| Additional Siting costs |  |  |  | 550000 |  | 0
| Additional Environmental costs |  |  |  | 450000 |  | 0
| Contaminated soil removal |  |  |  | 500000 |  | 0
Note on H18: Priors include all costs to date prior to estimate date
15 MW/20MWhr Battery Energy Storage System (BESS) - Cummings Hwy, Hyde Park SS #496, Boston MA.
Installlation of self contained battery enclosure
Installation of Power Conversion system (PCS) units
Installation of Step up transformers
Installation of MV Switchgear
Installation of underground ductbank to Manhole connection to grid.
Installation of sound mitigation
Installation of fire suppression systems
Installation of grounding transformer and grounding grid
Site development to incude fencing and lighting
Updated PAF to 2024.
ISD is 4/23/2027 based on schedule provided by PMT.
Prior costs for WO# 80089926 are included as of 12/31/2023.
Location is Eversource property, footprint of BESS property will not impede furture projects on this site.
Labor and material was taken from company #3 out of the 5 on the BESS indicative pricing sheet, dated 7/28/2023, provided by PMT.
Spot generation in two locations for load loss during construction.
Construction to be external vendor.
Engineering to be external with internal oversight.
Initial testing and commisioning will be by external vendor.
Initial training by external vendor
Maintenance and upkeep of BESS is not included.

## Delta
Project Title: Battery Storage - Hyde Park
Estimate #: E-23-373
Project Title: Battery Storage - Hyde Park
Project Number: 21334
WO & Task #: 80089926
Date of Estimate:12/08/2023
Estimate revision #: 00
Template Revision # 01.92a | 0
| Current Estimate | [9 empty] | Delta, Current - Previous Estimate |  | Notes
| MHRS | DOLLARS | MHRS | DOLLARS | MHRS | DOLLARS | MHRS | DOLLARS | MHRS | DOLLARS | MHRS | DOLLARS
CSTXX-CONSTRUCTION
Electrical Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Construction | 0 | 10963.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10963.25
SCADA / Automation | 160 | 11435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 11435
Other ( specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Reps ( internal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support Switch/Tag | 40 | 2921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2921
Other ( specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other ( specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other ( specify) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LT Total | 200 | 25319.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 25319.25
Employee Expenses | 0 | 717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 717
Constr. Purchased Mat'l (Eversource) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Constr. Purchased Mat'l (contracted) | 0 | 31928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31928
Outside Construction Vendor | 28237.7963 | 6385933.9772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28237.7963 | 6385933.9772
Sales tax on Constr. Vendor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicles ( now in indirects section) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inspection services ( Outside Vendor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Rep (Outside vendor) | 2762 | 475792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2762 | 475792
Rents and Leases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSTXX Subtotal | 31199.7963 | 6919690.2272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31199.7963 | 6919690.2272
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSTXX Total | 31199.7963 | 6919690.2272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31199.7963 | 6919690.2272
ENRXX-TG ENGINEERING/DESIGN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Services/Drafting | 380 | 26536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 26536
T- Line Engineering/Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D- Street Engineering/Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil Engineering/Design | 120 | 8240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 8240
Substation (T) Engineering/Design | 360 | 23931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 23931
Substation (D) Engineering/Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Protection & Controls Engineering | 880 | 60151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 60151
Survey Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Automation Engineering | 280 | 19962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 19962
Telecom Engineering | 80 | 5638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 5638
Other - specify | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other - specify | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LT Total | 2100 | 144458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 144458
Employee Expenses | 0 | 6960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6960
Contractor Engineering - T-Lines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor Engineering - D-Street | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor Engineering - T -Station | 1680 | 292300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 292300
Contractor Engineering - D-Station | 240 | 41082.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 41082.06
Contractor Engineering - P&C | 1200 | 208666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 208666
Contractor Engineering - Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor Engineering - SCADA / Automation | 320 | 55104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 55104
Contractor Engineering - Telecom | 240 | 41126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 41126
Contractor Engineering - Specify | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor Engineering - Specify | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor Engineering - Specify | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicles ( now in indirects section) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENRXX Subtotal | 5780 | 789696.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5780 | 789696.06
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENRXX Total | 5780 | 789696.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5780 | 789696.06
LNDXX-TG LAND | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Employee Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purchase Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicles ( now in indirects section) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fees and Payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LNDXX Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LNDXX Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MATXX-TG MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Eversource | 0 | 13761765.2117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13761765.2117
Outside Services | 0 | 1576.1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576.1039
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Freight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales Tax (Eversouce) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales Tax (outside services) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MATXX Subtotal | 0 | 13763341.3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13763341.3156
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MATXX Total | 0 | 13763341.3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13763341.3156
PSMXX-PROJECT MANAGER & SUPPORT
Project Management (PM) | 2888 | 199907.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2888 | 199907.53
Project Planning/Cost (IP) | 120 | 5884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 5884
Contracts/Purchasing (C/P) | 120 | 8291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 8291
System Planning | 40 | 2940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2940
Environmental | 320 | 269250.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 269250.05
SCS - Campaign | 0 | 54781.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54781.62
Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimating | 0 | 4880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4880
Siting - Chapter 40A | 0 | 25283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25283
Asset Management | 40 | 2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2407
Veg. Mgmt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LT Total | 3528 | 573624.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528 | 573624.2
Employee Expenses | 0 | 25070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25070
Project Support Vendor - PM | 4360 | 788344.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360 | 788344.62
Project Support Vendor - IP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - C/P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - System Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Enviromental | 141.12 | 40787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.12 | 40787
Project Support Vendor - SCS - Campaign | 0 | 220656.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220656.5
Project Support Vendor - Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Siting - Chapter 40A | 0 | 227166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227166
Project Support Vendor - Asset Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Veg. Mgmt. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Support Vendor - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicles ( now in indirects section) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Property or CWIP tax large proj. allowance | 0 | 939527.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939527.77
Builder All risk insurance excluding deductables( if project is over $50m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fees and Payments - Enviromental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fees and Payments - Siting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fees and Payments - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSMXX Subtotal | 8029.12 | 2815176.09 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2815176.09
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
journal entry adj | 0 | -4620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4620
PSMXX Total | 8029.12 | 2810556.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2810556.09
REMXX-TG REMOVAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering/Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Internal Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LT Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Employee Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outside Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicles ( now in indirects section) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rents and Leases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REMXX Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REMXX Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TSTXX-TG TEST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test / Field Engr. Labor (In House) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test / Comm. Engr. Labor (In House) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lead Commissioning Engr. (LCE) ( internal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Employee Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test / Field Engr. Labor (contractor) | 3200 | 701632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 701632
Test / Comm. Engr. Labor (contractor) | 1650 | 362202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 362202
Lead Commissioning Engr. (LCE) (contactor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vehicles ( now in indirects section) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TSTXX Subtotal | 0 | 1063834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063834
Escalation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TSTXX Total | 4850 | 1063834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4850 | 1063834
SUBTOTAL PROJECT DIRECT COST | 49858.9163 | 25347117.6928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41829.7963 | 25347117.6928
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk | 0 | 3950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950000
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Total | 0 | 3950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950000
TOTAL PROJECT DIRECT COST | 49858.9163 | 29297117.6928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41829.7963 | 29297117.6928
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INDIRECTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Productive Time Allocation (ZNP) | 0 | 122892.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122892.89
Payroll Benefits Allocation (ZPB) incl NPT | 0 | 14616.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14616.81
Gen SVC CO Overhead (ZGS) incl NPT | 0 | 410328.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410328.06
E&S Allocations (ZEB,ZEL,ZES) | 0 | 7085099.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7085099.95
AS&E Allocations (ZAS) | 0 | 298212.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298212.42
Stores Expense Allocation (ZST) | 0 | 712989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712989
Lobby Stock | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDEC (ZMI) | 0 | 739741.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739741.6
Vehicles (ZVE) | 0 | 138717.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138717.08
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirects Subtotal | 0 | 9522597.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9522597.81
TOTAL PROJECT COST - Direct & Indirect ( excl AFUDC ) | 49858.9163 | 38819715.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41829.7963 | 38819715.5028
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFUDC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFUDC (ZK) | 0.7 | 3298581.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 3298581.34
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFUDC Subtotal | 0.7 | 3298581.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 3298581.34
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT COST - Baseline Budget | 49859.6163 | 42118296.8428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41830.4963 | 42118296.8428
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingecy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | 0 | 1807885.5705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807885.5705
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency SubTotal | 0 | 1807885.5705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807885.5705
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT COST - Approved Funding | 49859.6163 | 43926182.4133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41830.4963 | 43926182.4133
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reimbursables / Customer Contribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reimbursables / Customer Contribution ( enter as negative) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PROJECT COST | 49859.6163 | 43926182.4133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41830.4963 | 43926182.4133
| Check total ( to detail summary tab) | 43926182.4133
0

## PAF Summary
| Project Number: 21334 |  | Project Title: Battery Storage - Hyde Park
|  |  |  | PAF (dollars in thousands) |  |  |  |  | And on years
|  |  |  | 2024-01-01 | 2025-01-01 | 2026-01-01 | 2027-01-01 | 2028-01-01 | 2029-01-01 | Total
| Line item Category | Prior Authorized | Actuals to Date | to Go
1 | 1. ROW / Easements / Land purchases |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2. Environmental Approvals / Permits |  | 5.0601 | 9.175 | 74.732 | 102.591 | 118.479 | 0 | 0 | 310.037
3 | 3. Outreach |  | 10.9681 | 0 | 46.797 | 63.037 | 123.92 | 30.716 | 0 | 275.4381
4 | 4. Siting Approvals / Permits |  | 10.307 | 0 | 42.623 | 57.767 | 113.601 | 28.151 | 0 | 252.449
5 | 5. Engineering / Design |  | 16.4241 | 0 | 330.74 | 390.211 | 17.431 | 34.89 | 0 | 789.6961
6 | 6. Materials ( Eversource purchased) |  | 2.358 | 0 | 4449.4017 | 4678.3947 | 4631.6108 | 0 | 0 | 13761.7652
7 | 7. Construction ( incl materials by contractors) |  | 10.9633 | 0 | 0.50985 | 0.53581 | 5136.5365 | 1772.721 | 0 | 6921.2663
8 | 8. Testing / Commissioning |  | 0 | 0 | 0 | 0 | 311.502 | 752.332 | 0 | 1063.834
9 | 9. PMT Project Mgmt Team |  | 74.2621 | 8.391 | 36.545 | 133.602 | 404.24 | 380.684 | 0 | 1037.7242
10 | 10. Removals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 11. Other ( property taxes and BAR) |  | 6.474 | 4.217 | 102.8438 | 260.005 | 561.368 | 0 | 0 | 934.9078
12 | 12. Risks |  | 0 | 0 | 0 | 900 | 1650 | 1400 | 0 | 3950
| Project Directs Total w/Risks | 0 | 136.8166 | 21.783 | 5084.1923 | 6586.1435 | 13068.6882 | 4399.494 | 0 | 29297.1177
13 | 13. Indirects/Overhead |  | 209.0808 | 40.387 | 754.365 | 956.615 | 5181.507 | 2380.643 | 0 | 9522.5978
14 | 14. AFUDC |  | 25.3743 | 2.791 | 228.093 | 723.923 | 1660.9 | 657.5 | 0 | 3298.5813
| Project Total - Baseline Budget | 0 | 371.2718 | 64.961 | 6066.6503 | 8266.6815 | 19911.0952 | 7437.637 | 0 | 42118.2968
15 | 15. Contingency |  | 0 | 1.046 | 458.0061 | 481.9973 | 747.9768 | 118.8594 | 0 | 1807.8856
0 | #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Total - Funding Approval Level | 0 | 371.2718 | 66.007 | 6524.6564 | 8748.6789 | 20659.072 | 7556.4963 | 0 | 43926.1824
16 | 16. Reimbursables/Customer Contribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Total (less reimbursables) | 0 | 371.2718 | 66.007 | 6524.6564 | 8748.6789 | 20659.072 | 7556.4963 | 0 | 43926.1824
| Total O&M |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL REQUEST | 0 | 371.2718 | 66.007 | 6524.6564 | 8748.6789 | 20659.072 | 7556.4963 | 0 | 43926.1824
| Breakout costs incl above |  |  | PAF (dollars in thousands)
1 | ST Labor | 0 | 88.4625 | 14.946 | 135.019 | 191.482 | 190 | 123.492 | 0 | 743.4014
2 | OT Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Outside services - Labor | 0 | 39.5222 | 1.873 | 389.666 | 546.151 | 6001.912 | 2861.668 | 0 | 9840.7922
4 | Materials ( All materials incl. outside service purchased which is shown in constr. above) | 0 | 2.358 | 0 | 4449.9115 | 4678.9305 | 4655.9092 | 8.16 | 0 | 13795.2693
5 | Removals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Other | 0 | 6.474 | 6.01 | 567.6019 | 1651.5773 | 2968.8438 | 1525.0334 | 0 | 6725.5403
7 | Indirects | 0 | 209.0808 | 40.387 | 754.365 | 956.615 | 5181.507 | 2380.643 | 0 | 9522.5978
8 | AFUDC | 0 | 25.3743 | 2.791 | 228.093 | 723.923 | 1660.9 | 657.5 | 0 | 3298.5813
| TOTAL CAPITAL REQUEST - with out Reimbursables | 0 | 371.2718 | 66.007 | 6524.6564 | 8748.6789 | 20659.072 | 7556.4963 | 0 | 43926.1824
0
Notes from EPAC Administrators: To copy and paste this WBS Project Cost Summary table into the PAF form, follow these steps:
Navigate to the worksheet "PAF Summary WBS" in the estimating workbook (this worksheet)
Select MS Excel cells C5:K28 (the entire table except for the row and column headers)
Click copy in MS Excel
in the MS Word PAF file, navigate to the Project Cost Summary table on page 2
Select all of the "$"s in the table (the entire table except for the row and column headers)
In the MS Word PAF file, click on the down arrow under the Paste button, then click on "Paste Special", then select "Unformatted Text", and then click "OK".
Notes from EPAC Administrators: To copy and paste this Breakout Costs table into the PAF form, follow these steps:
Navigate to the worksheet "PAF Summary WBS" in the estimating workbook (this worksheet)
Select MS Excel cells C31:K39 (the entire table except for the row and column headers)
Click copy in MS Excel
in the MS Word PAF file, navigate to the Breakout Costs table on page 3
Select all of the "$"s in the table (the entire table except for the row and column headers)
In the MS Word PAF file, click on the down arrow under the Paste button, then click on "Paste Special", then select "Unformatted Text", and then click "OK".

## ISO comparison table
| Project Number: 21334 |  | Project Title: Battery Storage - Hyde Park
| WO & Task #: 80089926 | (dollars in thousands)
| ISO / TCA Comparision Table | 0 | Date | Date
|  | Total Estimate | PAC (+50/-25%) | TCA (+10/-10%)
Scope ( Qty)
1 | 1. ROW / Easements / Land purchases | 0
2 | 2. Environmental Approvals / Permits | 310.037
3 | 3. Outreach | 275.4381
4 | 4. Siting Approvals / Permits | 252.449
5 | 5. Engineering / Design | 789.6961
6 | 6. Materials ( Eversource purchased) | 13761.7652
7 | 7. Construction ( incl materials by contractors) | 6921.2663
8 | 8. Testing / Commissioning | 1063.834
9 | 9. PMT Project Mgmt Team | 1037.7242
10 | 10. Removals | 0
11 | 11. Other ( property taxes and BAR) | 934.9078
12 | 12. Risks | 3950
| Project Directs Total w/Risks | 29297.1177 | 0 | 0 | 0
13 | 13. Indirects/Overhead | 9522.5978
14 | 14. AFUDC | 3298.5813
| Project Total - Baseline Budget | 42118.2968 | 0 | 0 | 0
15 | 15. Contingency | 1807.8856
| Project Total - Funding Approval Level | 43926.1824 | 0 | 0 | 0
16 | 16. Reimbursables/Customer Contribution | 0
| Project Total (less reimbursables) | 43926.1824 | 0 | 0 | 0
Old ISO / TCA Comparison Table
|  | 0 | Date | Date | 0
| $x 1000 | Total Estimate | PAC (+50/-25%) | TCA (+10/-10%) | 0
| Scope (qty) |  | 0 | 0 | 0
1 | Construction | 6079.3 | 0 | 0 | 0
2 | Engineering/PM/Siting | 734.4 | 0 | 0 | 0
3 | Land | 0 | 0 | 0 | 0
4 | Material ( all materials) | 13126.9 | 0 | 0 | 0
5 | Project Mgmt. & Sppt. | 2541.6 | 0 | 0 | 0
6 | Removal | 0 | 0 | 0 | 0
7 | Test | 926.4
8 | Contingency | 5753.3
9 | Escalation | 2960.1
10 | Indirects | 8505.6
11 | AFUDC | 3298.6
| Grand Total | 43926.2 | 0 | 0 | 0
| Difference Percentage |  | 0% | 0%

## Unit Comparison
| Dollars in Thousands |  | Dollars in Thousands
Line item Category | Normalized Program Cost | Program Unit Cost | Estimate Total Cost | Estimate Unit Cost | Delta
Notes
Location / project number
Units |  | 4 |  | 1
1. ROW / Easements / Land purchases |  | 0 | 0 | 0 | 0
2. Environmental Approvals / Permits |  | 0 | 310.037 | 310.037 | 310.037
3. Outreach |  | 0 | 275.4381 | 275.4381 | 275.4381
4. Siting Approvals / Permits |  | 0 | 252.449 | 252.449 | 252.449
5. Engineering / Design |  | 0 | 789.6961 | 789.6961 | 789.6961
6. Materials ( Eversource purchased) |  | 0 | 13761.7652 | 13761.7652 | 13761.7652
7. Construction ( incl matl's by contractors) |  | 0 | 6921.2663 | 6921.2663 | 6921.2663
8. Testing / Commissioning |  | 0 | 1063.834 | 1063.834 | 1063.834
9. PMT Project Mgmt Team |  | 0 | 1037.7242 | 1037.7242 | 1037.7242
10. Removals |  | 0 | 0 | 0 | 0
11. Other |  | 0 | 934.9078 | 934.9078 | 934.9078
12. Risks |  | 0 | 3950 | 3950 | 3950
Project Directs Total w/Risks |  | 0 | 29297.1177 | 29297.1177 | 29297.1177
13. Indirects/Overhead |  | 0 | 9522.5978 | 9522.5978 | 9522.5978
14. AFUDC |  | 0 | 3298.5813 | 3298.5813 | 3298.5813
Project Total - Baseline Budget |  | 0 | 42118.2968 | 42118.2968 | 42118.2968
15. Contingency |  | 0 | 1807.8856 | 1807.8856 | 1807.8856
#N/A |  | 0 | 0 | 0 | 0
Project Total - Funding Approval Level |  | 0 | 43926.1824 | 43926.1824 | 43926.1824
16. Reimbursables/Customer Contribution |  | 0 | 0 | 0 | 0
#N/A |  | 0 | 0 | 0 | 0
Project Total (less reimbursables) |  | 0 | 43926.1824 | 43926.1824 | 43926.1824
Total O&M |  | 0 | 0 | 0 | 0
TOTAL REQUEST |  | 0 | 43926.1824 | 43926.1824 | 43926.1824
Breakout costs incl above
ST Labor |  | 0 | 743.4014 | 743.4014 | 743.4014
OT Labor |  | 0 | 0 | 0 | 0
Outside services - Labor |  | 0 | 9840.7922 | 9840.7922 | 9840.7922
Materials ( All materials incl. outside service purchased which is shown in constr. above) |  | 0 | 13795.2693 | 13795.2693 | 13795.2693
Removals |  | 0 | 0 | 0 | 0
Other |  | 0 | 6725.5403 | 6725.5403 | 6725.5403
Indirects |  | 0 | 9522.5978 | 9522.5978 | 9522.5978
AFUDC |  | 0 | 3298.5813 | 3298.5813 | 3298.5813
TOTAL CAPITAL REQUEST - with out Reimbursables |  | 0 | 43926.1824 | 43926.1824 | 43926.1824

## PP4 Estimate and Schedule
PROJECT COST ESTIMATE & SCHEDULE SHEET
Transmission Owner: |  | Eversource Energy |  |  |  | Project Number: T12345
Project Name: |  | Battery Storage - Hyde Park |  |  |  | In Service date (ISD):04/23/2027
Estimate Grade: |  | Conceptual
1. Project Scope Summary
2. Project Cost Summary
Prior Estimated Cost:
2.1. Project Cost Summary
|  | PTF | Non-PTF | Total
| Material | 15172.5295 |  | 15172.5295
| Labor & Equipment | 12449.5255 |  | 12449.5255
| Right of Way | 0 |  | 0
| Engineering/Permitting /Indirects | 4377.1729 |  | 4377.1729
| Escalation | 2960.2 |  | 2960.2
| AFUDC | 3298.6 |  | 3298.6
| Contingency | 5757.9 |  | 5757.9
| Total Project Cost | 44015.928 | 0 | 44015.928
2.2 Detailed Cost Summary By Project Element
|  | Material | Labor & Equip. | Right of Way | Engineering/ Permitting/ Indirects | Escalation | AFUDC | Contingency | Total
|  | 15172.5295 | 12449.5255 | 0 | 4377.1729 | 2960.2 | 3298.6 | 5757.9 | 44015.928
| Total | 15172.5295 | 12449.5255 | 0 | 4377.1729 | 2960.2 | 3298.6 | 5757.9 | 44015.928
Note: Values expressed in $1k
3. Project Milestone Schedule

## Detail Summary
[5 empty] | 0 | [42 empty] | 0 | [40 empty] | 0
[5 empty] | 0 | [42 empty] | 0 | [40 empty] | 0
[10 empty] | Escalated Line Item Dollars | [37 empty] | UNESCALATED LINE ITEM DOLLARS | [40 empty] | Escalation $'s | [7 empty] | 0% |  |  | 5% |  |  | 9.2% |  |  | 12.48% |  |  | 15.85% |  |  | 19.33% |  |  | 22.91% |  |  | 26.59% |  |  | 30.39% |  |  | 34.3% |  | compounded lab escal
[5 empty] | Project Number: 21334 | [42 empty] | Project Number: 21334 | [48 empty] | 0% |  |  | 3% |  |  | 5.06% |  |  | 7.161% |  |  | 9.304% |  |  | 11.49% |  |  | 13.72% |  |  | 15.99% |  |  | 18.31% |  |  | 20.68% |  | compounded mat'l escal
[5 empty] | Date of Estimate:12/08/2023 | [42 empty] | Date of Estimate:12/08/2023 | [48 empty] | 0% |  |  | 5% |  |  | 4% |  |  | 3% |  |  | 3% |  |  | 3% |  |  | 3% |  |  | 3% |  |  | 3% |  |  | 3% |  | per annun
[5 empty] | Estimate revision #: 00 | [42 empty] | Estimate revision #: 00
[5 empty] | Template Revision # 01.92a | 0% | [6 empty] | 0 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  |  |  | Check Calc |  |  | Escalation Rate | 0% |  |  | E Rate | 57 | [5 empty] | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 | [16 empty] | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9
[9 empty] | Prior actuals to date |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  |  | 2029-01-01 |  |  | 2030-01-01 |  |  | 2031-01-01 |  |  | 2032-01-01 |  |  | 2033-01-01 |  |  | TOTAL | [9 empty] | Prior |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  |  | 2029-01-01 |  |  | 2030-01-01 |  |  | 2031-01-01 |  |  | 2032-01-01 |  |  | 2033-01-01 |  |  | TOTAL | [7 empty] | Prior |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  | 0 | 2029-01-01 |  | 0 | 2030-01-01 |  | 0 | 2031-01-01 |  | 0 | 2032-01-01 |  | 0 | 2033-01-01 |  |  | TOTAL
[9 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS | [8 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS | Notes | [5 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS | Mhrs | DOLLARS | DOLLARS | Mhrs | DOLLARS | DOLLARS | Mhrs | DOLLARS | DOLLARS | Mhrs | DOLLARS | DOLLARS | Mhrs | DOLLARS | DOLLARS |  | Mhrs | DOLLARS
PAF (old) | Cover (old) | PAF (breakout tbl) | WBS | Indirects | CSTXX-CONSTRUCTION | R | [41 empty] | CSTXX-CONSTRUCTION | R | [39 empty] | CSTXX-CONSTRUCTION | R
1 | 1 | 1 | 7 | E&S | Electrical Construction | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Electrical Construction | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Electrical Construction | LT |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
1 | 1 | 1 | 7 | E&S | General Construction | LT | 4670% |  | 0 | 10963.25 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10963.25 |  | 10963.25 |  |  | General Construction | LT | 46.7 |  | 0 | 10963.25 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 10963.25 |  |  | General Construction | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
1 | 1 | 1 | 7 | E&S | SCADA / Automation | LT | 6260% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 80 | 5633 |  | 80 | 5802 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 160 | 11435 |  | 11435 |  |  | SCADA / Automation | LT | 62.6 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 80 | 5008 |  | 80 | 5008 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 160 | 10016 | Commisioning Support |  | SCADA / Automation | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 625 |  | 0 | 794 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1419 | 0
1 | 1 | 1 | 7 | E&S | Other ( specify) | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other ( specify) | LT | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Other ( specify) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
1 | 1 | 1 | 7 | E&S | Construction Reps ( internal) | LT | 5940% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Construction Reps ( internal) | LT | 59.4 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Construction Reps ( internal) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 1 | 1 | 7 | E&S | Support Switch/Tag | LT | 6303% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2921 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2921 |  | 2921 |  |  | Support Switch/Tag | LT | 63.03 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2521 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 40 | 2521 | interconnection to grid switch time |  | Support Switch/Tag | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 400 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 400
1 | 1 | 1 | 7 | E&S | Other ( specify) | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other ( specify) | LT | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Other ( specify) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 1 | 1 | 7 | E&S | Other ( specify) | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other ( specify) | LT | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Other ( specify) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 1 | 1 | 7 | E&S | Other ( specify) | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other ( specify) | LT | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Other ( specify) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | LT Total |  | 0% |  | 0 | 10963.25 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 80 | 5633 |  | 120 | 8723 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 200 | 25319.25 |  | 25319.25 |  |  | LT Total |  |  |  | 0 | 10963.25 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 80 | 5008 |  | 120 | 7529 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 200 | 23500.25 |  |  | LT Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 625 |  | 0 | 1194 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1819
5 | 1 | 6 | 7 |  | Employee Expenses | AE | 5% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 281 |  |  | 436 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 717 |  | 717 |  |  | Employee Expenses | AE | 5% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 250 |  |  | 376 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 626 |  |  | Employee Expenses | AE |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 31 |  | 0 | 60 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 91
4 | 4 | 4 | 6 |  | Constr. Purchased Mat'l (Eversource) | AM | 1% | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | Constr. Purchased Mat'l (Eversource) | AM | 1% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Constr. Purchased Mat'l (Eversource) | AM |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | 4 | 4 | 7 |  | Constr. Purchased Mat'l (contracted) | AM | 0.5% | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 23768 |  |  | 8160 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 31928 |  | 31928 |  |  | Constr. Purchased Mat'l (contracted) | AM | 0.5% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 21132 |  |  | 7044 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 28176 |  |  | Constr. Purchased Mat'l (contracted) | AM |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 2636 |  | 0 | 1116 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3752
3 | 1 | 3 | 7 | OS | Outside Construction Vendor | AQ |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 21178.3473 | 4753797.0059 |  | 7059.4491 | 1632136.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 28237.7963 | 6385933.9772 |  | 6385933.9772 |  |  | Outside Construction Vendor | AQ |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 21178.3473 | 4226499 |  | 7059.4491 | 1408833 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 28237.7963 | 5635332 | 275 crew days based on 10 man crew 10 hr days |  | Outside Construction Vendor | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 527298.0059 |  |  | 223303.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 750601.9772
5 | 1 | 6 | 7 |  | Sales tax on Constr. Vendor |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | Sales tax on Constr. Vendor |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Sales tax on Constr. Vendor |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 1 | 6 | 7 |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Vehicles ( now in indirects section) | AV |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 1 | 3 | 7 | OS | Inspection services ( Outside Vendor) | AQ |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Inspection services ( Outside Vendor) | AQ | 152 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Inspection services ( Outside Vendor) | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 1 | 3 | 7 | OS | Construction Rep (Outside vendor) | AQ |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2062 | 352527 |  | 700 | 123265 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2762 | 475792 |  | 475792 |  |  | Construction Rep (Outside vendor) | AQ | 152 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2062 | 313424 |  | 700 | 106400 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2762 | 419824 | based on crew days and an 10 hour day |  | Construction Rep (Outside vendor) | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 39103 |  | 0 | 16865 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 55968
5 | 1 | 6 | 7 |  | Rents and Leases | BR |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | Rents and Leases | BR |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Rents and Leases | BR |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | CSTXX Subtotal |  |  |  |  | 10963.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5136006.0059 |  |  | 1772720.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6919690.2272 |  | 6919690.2272 |  |  | CSTXX Subtotal |  |  |  |  | 10963.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 4566313 |  |  | 1530182 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6107458.25 |  |  | CSTXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 569693.0059 |  |  | 242538.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 812231.9772
| 9 |  | 99 |  | Escalation |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Escalation |  |  |  |  | 0 | [31 empty] | 0 | 0
5 | 8 | 6 | 11 |  | 0 | P1 | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 | P1 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | CSTXX Total |  |  |  | 0 | 10963.25 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 23320.3473 | 5136006.0059 |  | 7879.4491 | 1772720.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 31199.7963 | 6919690.2272 |  | 6919690.2272 |  |  | CSTXX Total |  |  |  | 0 | 10963.25 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 23320.3473 | 4566313 |  | 7879.4491 | 1530182 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 31199.7963 | 6107458.25 |  |  | CSTXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 569693.0059 |  | 0 | 242538.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 812231.9772
[5 empty] | ENRXX-TG ENGINEERING/DESIGN | [36 empty] | 0 | 0 |  | 0 |  |  | ENRXX-TG ENGINEERING/DESIGN | [36 empty] | 0 | 0 |  |  | ENRXX-TG ENGINEERING/DESIGN | [36 empty] | 0 | 0
1 | 2 | 1 | 5 | E&S | Project Services/Drafting | LT | 6370% |  | 0 | 0 |  | 0 | 0 |  | 120 | 8026 |  | 160 | 11130 |  | 0 | 0 |  | 100 | 7380 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 380 | 26536 |  | 26536 |  |  | Project Services/Drafting | LT | 63.7 |  | 0 | 0 |  |  | 0 |  | 120 | 7644 |  | 160 | 10192 |  | 0 | 0 |  | 100 | 6370 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 380 | 24206 |  |  | Project Services/Drafting | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 382 |  | 0 | 938 |  | 0 | 0 |  | 0 | 1010 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2330
1 | 2 | 1 | 5 | E&S | T- Line Engineering/Design | LT | 6370% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | T- Line Engineering/Design | LT | 63.7 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | T- Line Engineering/Design | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 2 | 1 | 5 | E&S | D- Street Engineering/Design | LT | 6370% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | D- Street Engineering/Design | LT | 63.7 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | D- Street Engineering/Design | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 2 | 1 | 5 | E&S | Civil Engineering/Design | LT | 6370% |  | 0 | 0 |  | 0 | 0 |  | 40 | 2675 |  | 80 | 5565 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 120 | 8240 |  | 8240 |  |  | Civil Engineering/Design | LT | 63.7 |  | 0 | 0 |  |  | 0 |  | 40 | 2548 |  | 80 | 5096 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 120 | 7644 | 3 weeks for review |  | Civil Engineering/Design | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 127 |  | 0 | 469 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 596
1 | 2 | 1 | 5 | E&S | Substation (T) Engineering/Design | LT | 6150% |  | 0 | 5269 |  | 0 | 0 |  | 120 | 2217 |  | 160 | 10745 |  | 0 | 0 |  | 80 | 5700 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 360 | 23931 |  | 23931 |  |  | Substation (T) Engineering/Design | LT | 61.5 |  | 0 | 5269 |  | 0 | 0 |  | 120 | 2111 |  | 160 | 9840 |  | 0 | 0 |  | 80 | 4920 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 360 | 22140 | Review hours |  | Substation (T) Engineering/Design | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 106 |  | 0 | 905 |  | 0 | 0 |  | 0 | 780 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1791
1 | 2 | 1 | 5 | E&S | Substation (D) Engineering/Design | LT | 6150% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Substation (D) Engineering/Design | LT | 61.5 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Substation (D) Engineering/Design | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 2 | 1 | 5 | E&S | Protection & Controls Engineering | LT | 6150% |  | 0 | 0 |  | 0 | 0 |  | 160 | 10332 |  | 240 | 16118 |  | 240 | 16601 |  | 240 | 17100 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 880 | 60151 |  | 60151 |  |  | Protection & Controls Engineering | LT | 61.5 |  | 0 | 0 |  |  | 0 |  | 160 | 9840 |  | 240 | 14760 |  | 240 | 14760 |  | 240 | 14760 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 880 | 54120 | Evaluation and review of P&C provided by PMT |  | Protection & Controls Engineering | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 492 |  | 0 | 1358 |  | 0 | 1841 |  | 0 | 2340 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6031
1 | 2 | 1 | 5 | E&S | Survey Engineering | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Survey Engineering | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Survey Engineering | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 2 | 1 | 5 | E&S | SCADA / Automation Engineering | LT | 6580% |  | 0 | 0 |  | 0 | 0 |  | 120 | 8291 |  | 120 | 8622 |  | 0 | 0 |  | 40 | 3049 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 280 | 19962 |  | 19962 |  |  | SCADA / Automation Engineering | LT | 65.8 |  | 0 | 0 |  | 0 | 0 |  | 120 | 7896 |  | 120 | 7896 |  | 0 | 0 |  | 40 | 2632 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 280 | 18424 | teelcom review hours |  | SCADA / Automation Engineering | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 395 |  | 0 | 726 |  | 0 | 0 |  | 0 | 417 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1538
1 | 2 | 1 | 5 | E&S | Telecom Engineering | LT | 6580% |  | 0 | 0 |  | 0 | 0 |  | 40 | 2764 |  | 40 | 2874 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 80 | 5638 |  | 5638 |  |  | Telecom Engineering | LT | 65.8 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2632 |  | 40 | 2632 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 80 | 5264 |  |  | Telecom Engineering | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 132 |  | 0 | 242 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 374
1 | 2 | 1 | 5 | E&S | Other - specify | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other - specify | LT | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Other - specify | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 2 | 1 | 5 | E&S | Other - specify | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other - specify | LT | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Other - specify | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | LT Total |  | 0% |  | 0 | 5269 |  | 0 | 0 |  | 600 | 34305 |  | 800 | 55054 |  | 240 | 16601 |  | 460 | 33229 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2100 | 144458 |  | 144458 |  |  | LT Total |  |  |  | 0 | 5269 |  | 0 | 0 |  | 600 | 32671 |  | 800 | 50416 |  | 240 | 14760 |  | 460 | 28682 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2100 | 131798 |  |  | LT Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 1634 |  | 0 | 4638 |  | 0 | 1841 |  | 0 | 4547 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12660
5 | 2 | 6 | 5 |  | Employee Expenses | AE | 5% |  | 0 | 0 |  | 0 | 0 |  | 0 | 1716 |  | 0 | 2753 |  | 0 | 830 |  | 0 | 1661 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6960 |  | 6960 |  |  | Employee Expenses | AE | 5% |  | 0 | 0 |  |  | 0 |  |  | 1634 |  |  | 2521 |  |  | 738 |  |  | 1434 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 6327 |  |  | Employee Expenses | AE |  |  |  | 0 |  |  | 0 |  |  | 82 |  |  | 232 |  | 0 | 92 |  | 0 | 227 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 633
3 | 2 | 3 | 5 | OS | Contractor Engineering - T-Lines | AQ | 16100% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Engineering - T-Lines | AQ | 161 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Engineering - T-Lines | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 2 | 3 | 5 | OS | Contractor Engineering - D-Street | AQ | 16100% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Engineering - D-Street | AQ | 161 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Engineering - D-Street | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 2 | 3 | 5 | OS | Contractor Engineering - T -Station | AQ | 16200% |  | 0 | 0 |  | 0 | 0 |  | 720 | 122472 |  | 960 | 169828 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1680 | 292300 |  | 292300 |  |  | Contractor Engineering - T -Station | AQ | 162 |  | 0 | 0 |  | 0 | 0 |  | 720 | 116640 |  | 960 | 155520 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1680 | 272160 | external vendor station design, system integration and layout, 42 weeks |  | Contractor Engineering - T -Station | AQ |  |  |  | 0 |  |  | 0 |  |  | 5832 |  |  | 14308 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20140
3 | 2 | 3 | 5 | OS | Contractor Engineering - D-Station | AQ | 16200% |  | 0 | 11155.06 |  | 0 | 0 |  | 120 | 8699 |  | 120 | 21228 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 240 | 41082.06 |  | 41082.06 |  |  | Contractor Engineering - D-Station | AQ | 162 |  | 0 | 11155.06 |  | 0 | 0 |  | 120 | 8284.94 |  | 120 | 19440 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 240 | 38880 | Review hours |  | Contractor Engineering - D-Station | AQ |  |  |  | 0 |  |  | 0 |  |  | 414.06 |  |  | 1788 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2202.06
3 | 2 | 3 | 5 | OS | Contractor Engineering - P&C | AQ | 16300% |  | 0 | 0 |  | 0 | 0 |  | 720 | 123228 |  | 480 | 85438 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1200 | 208666 |  | 208666 |  |  | Contractor Engineering - P&C | AQ | 163 |  | 0 |  |  | 0 | 0 |  | 720 | 117360 |  | 480 | 78240 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1200 | 195600 | 30 weeks for external vendor P&C planning and layout and relay settings; |  | Contractor Engineering - P&C | AQ |  |  |  | 0 |  |  | 0 |  |  | 5868 |  |  | 7198 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 13066
3 | 2 | 3 | 5 | OS | Contractor Engineering - Survey | AQ | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Engineering - Survey | AQ |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Engineering - Survey | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 2 | 3 | 5 | OS | Contractor Engineering - SCADA / Automation | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 120 | 20160 |  | 200 | 34944 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 320 | 55104 |  | 55104 |  |  | Contractor Engineering - SCADA / Automation | AQ | 160 |  | 0 | 0 |  | 0 | 0 |  | 120 | 19200 |  | 200 | 32000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 320 | 51200 | 8 weeks for scada settings and layout |  | Contractor Engineering - SCADA / Automation | AQ |  |  |  | 0 |  |  | 0 |  |  | 960 |  |  | 2944 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3904
3 | 2 | 3 | 5 | OS | Contractor Engineering - Telecom | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 120 | 20160 |  | 120 | 20966 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 240 | 41126 |  | 41126 |  |  | Contractor Engineering - Telecom | AQ | 160 |  | 0 | 0 |  | 0 | 0 |  | 120 | 19200 |  | 120 | 19200 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 240 | 38400 | 6 weeks for telecom, walk down layout and support |  | Contractor Engineering - Telecom | AQ |  |  |  | 0 |  |  | 0 |  |  | 960 |  |  | 1766 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2726
3 | 2 | 3 | 5 | OS | Contractor Engineering - Specify | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Engineering - Specify | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Engineering - Specify | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 2 | 3 | 5 | OS | Contractor Engineering - Specify | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Engineering - Specify | AQ | 160 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Engineering - Specify | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 2 | 3 | 5 | OS | Contractor Engineering - Specify | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Engineering - Specify | AQ | 160 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Engineering - Specify | AQ |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 2 | 3 | 5 |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Vehicles ( now in indirects section) | AV |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Vehicles ( now in indirects section) | AE |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | ENRXX Subtotal |  | 0% |  | 0 | 16424.06 |  | 0 | 0 |  | 2400 | 330740 |  | 2680 | 390211 |  | 240 | 17431 |  | 460 | 34890 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 789696.06 |  | 789696.06 |  |  | ENRXX Subtotal |  |  |  |  | 16424.06 |  |  | 0 |  |  | 314989.94 |  |  | 357337 |  |  | 15498 |  |  | 30116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 734365 |  |  | ENRXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 15750.06 |  |  | 32874 |  |  | 1933 |  |  | 4774 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 55331.06
| 9 |  | 99 |  | Escalation |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Escalation |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 8 | 6 | 11 |  | other | P1 | 0% |  | 0 | 7511.24 |  | 0 | 0 |  | 0 | -7511.24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | other |  | 0% |  | 0 | 7511.24 |  |  | 0 |  |  | -7511.24 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | other | P1 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | ENRXX Total |  | 0% |  | 0 | 23935.3 |  | 0 | 0 |  | 2400 | 323228.76 |  | 2680 | 390211 |  | 240 | 17431 |  | 460 | 34890 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 5780 | 789696.06 |  | 789696.06 |  |  | ENRXX Total |  |  |  | 0 | 23935.3 |  | 0 | 0 |  | 2400 | 307478.7 |  | 2680 | 357337 |  | 240 | 15498 |  | 460 | 30116 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 5780 | 734365 |  |  | ENRXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 15750.06 |  | 0 | 32874 |  | 0 | 1933 |  | 0 | 4774 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 55331.06
[5 empty] | LNDXX-TG LAND |  | 0% | [34 empty] | 0 | 0 |  | 0 |  |  | LNDXX-TG LAND | [36 empty] | 0 | 0 |  |  | LNDXX-TG LAND | [36 empty] | 0 | 0
1 | 3 | 1 | 1 | GSO | Real Estate | LT | 6470% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Real Estate | LT | 64.7 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Real Estate | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 3 | 6 | 1 |  | Employee Expenses | AE | 5% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Employee Expenses | AE | 5% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Employee Expenses | AE |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | 3 | 4 | 1 | LND | Purchase Land | AM | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Purchase Land | AM |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Purchase Land | AM |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | 3 | 4 | 1 | LND | Easements | AM | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Easements | AM |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Easements | AM |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 3 | 6 | 1 |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Vehicles ( now in indirects section) | AV |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 3 | 6 | 1 |  | Fees and Payments | BF | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Fees and Payments | BF |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Fees and Payments | BF |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | LNDXX Subtotal |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | LNDXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | LNDXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 9 |  | 99 |  | Escalation |  | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Escalation |  |  |  |  | 0 | [31 empty] | 0 | 0
5 | 8 | 6 | 11 |  | 0 | P1 | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 | P1 |  |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | LNDXX Total |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | LNDXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | LNDXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | MATXX-TG MATERIAL |  | 0% | [34 empty] | 0 | 0 |  | 0 |  |  | MATXX-TG MATERIAL | [36 empty] | 0 | 0 |  |  | MATXX-TG MATERIAL | [36 empty] | 0 | 0
4 | 4 | 4 | 6 |  | Eversource | AM | 0% |  | 0 | 2358 |  | 0 | 0 |  | 0 | 4449401.6937 |  | 0 | 4678394.7327 |  | 0 | 4631610.7853 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 13761765.2117 |  | 13761765.2117 |  |  | Eversource | AM |  |  | 0 | 2358 |  |  | 0 |  |  | 4319738.79 |  |  | 4453069.42 |  |  | 4322096.79 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 13097263 |  |  | Eversource | AM |  |  |  | 0 |  |  | 0 |  |  | 129662.9037 |  |  | 225325.3127 |  |  | 309513.9953 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 664502.2117
4 | 4 | 4 | 7 |  | Outside Services | AM | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 509.85 |  | 0 | 535.806 |  | 0 | 530.4479 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1576.1039 |  | 1576.1039 |  |  | Outside Services | AM |  |  | 0 |  |  |  | 0 |  |  | 495 |  |  | 510 |  |  | 495 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 1500 |  |  | Outside Services | AM |  |  |  | 0 |  |  | 0 |  |  | 14.85 |  |  | 25.806 |  |  | 35.4479 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 76.1039
4 | 4 | 4 |  |  |  | AM | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | AM |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  |  | AM |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 4 | 4 | 6 |  | Freight |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Freight |  | 0% |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Freight |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | 4 | 4 | 6 |  | Sales Tax (Eversouce) |  | 6.25% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Sales Tax (Eversouce) |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Sales Tax (Eversouce) |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
4 | 4 | 4 | 7 |  | Sales Tax (outside services) |  | #REF! |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Sales Tax (outside services) |  | 6.25% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Sales Tax (outside services) |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 4 | 4 | 6 |  | Other |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Other |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | MATXX Subtotal |  | 0% |  |  | 2358 |  |  | 0 |  |  | 4449911.5437 |  |  | 4678930.5387 |  |  | 4632141.2333 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13763341.3156 |  | 13763341.3156 |  |  | MATXX Subtotal |  |  |  |  | 2358 |  |  | 0 |  |  | 4320233.79 |  |  | 4453579.42 |  |  | 4322591.79 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13098763 |  |  | MATXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 129677.7537 |  |  | 225351.1187 |  |  | 309549.4433 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 664578.3156
| 9 |  | 99 |  | Escalation |  | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 | [7 empty] | 0 | [31 empty] | 0 | 0
5 | 8 | 6 | 11 |  | 0 | P1 | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 | P1 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | MATXX Total |  | 0% |  |  | 2358 |  |  | 0 |  |  | 4449911.5437 |  |  | 4678930.5387 |  |  | 4632141.2333 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 13763341.3156 |  | 13763341.3156 |  |  | MATXX Total |  |  |  |  | 2358 |  |  | 0 |  |  | 4320233.79 |  |  | 4453579.42 |  |  | 4322591.79 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 13098763 |  |  | MATXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 129677.7537 |  | 0 | 225351.1187 |  | 0 | 309549.4433 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 664578.3156
[5 empty] | PSMXX-PROJECT MANAGER & SUPPORT |  | 0% | [40 empty] | PSMXX-PROJECT MANAGER & SUPPORT | [37 empty] | 0 |  |  | PSMXX-PROJECT MANAGER & SUPPORT
1 | 5 | 1 | 9 | GSO | Project Management (PM) | LT | 6370% |  | 0 | 53954.53 |  | 120 | 7644 |  | 120 | 8026 |  | 416 | 28937 |  | 1248 | 28730 |  | 984 | 72616 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2888 | 199907.53 |  | 199907.53 |  |  | Project Management (PM) | LT | 63.7 |  | 0 | 53954.53 |  | 120 | 7644 |  | 120 | 7644 |  | 416 | 26499 |  | 1248 | 25543.47 |  | 984 | 62681 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 2888 | 183966 | 3 days per construction week and 8+ hours per week for lead up year +40 for close out |  | Project Management (PM) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 382 |  | 0 | 2438 |  | 0 | 3186.53 |  | 0 | 9935 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 15941.53
1 | 5 | 1 | 9 | GSO | Project Planning/Cost (IP) | LT | 4670% |  | 0 | 0 |  | 0 | 0 |  | 120 | 5884 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 120 | 5884 |  | 5884 |  |  | Project Planning/Cost (IP) | LT | 46.7 |  | 0 | 0 |  | 0 | 0 |  | 120 | 5604 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 120 | 5604 |  |  | Project Planning/Cost (IP) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 280 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 280
1 | 5 | 1 | 9 | GSO | Contracts/Purchasing (C/P) | LT | 6580% |  | 0 | 0 |  | 0 | 0 |  | 120 | 8291 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 120 | 8291 |  | 8291 |  |  | Contracts/Purchasing (C/P) | LT | 65.8 |  | 0 |  |  | 0 | 0 |  | 120 | 7896 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 120 | 7896 |  |  | Contracts/Purchasing (C/P) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 395 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 395
1 | 5 | 1 | 9 | GSO | System Planning | LT | 7000% |  | 0 | 0 |  | 0 | 0 |  | 40 | 2940 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2940 |  | 2940 |  |  | System Planning | LT | 70 |  | 0 |  |  |  | 0 |  | 40 | 2800 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2800 |  |  | System Planning | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 140 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 140
1 | 5 | 1 | 2 | GSO | Environmental | LT | 0% |  | 0 | 5060.05 |  | 16 | 7302 |  | 80 | 64901 |  | 105.6 | 89095 |  | 118.4 | 102892 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 320 | 269250.05 |  | 269250.05 |  |  | Environmental | LT |  |  | 0 | 5060.05 |  | 16 | 7301.95 |  | 80 | 61810 |  | 105.6 | 81589 |  | 118.4 | 91479 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 320 | 247240 |  |  | Environmental | LT |  |  | 0 | 0 |  | 0 | 0.05 |  | 0 | 3091 |  | 0 | 7506 |  | 0 | 11413 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 22010.05
1 | 5 | 1 | 3 | GSO | SCS - Campaign | LT | 0% |  | 0 | 8335.62 |  | 0 | 0 |  | 0 | 2910 |  | 0 | 12608 |  | 0 | 24784 |  | 0 | 6144 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 54781.62 |  | 54781.62 |  |  | SCS - Campaign | LT |  |  | 0 | 8335.62 |  |  | 0 |  | 0 | 2771.38 |  | 0 | 11546 |  | 0 | 22035 |  | 0 | 5303 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 49991 | as per Estimate request 7/28/23 |  | SCS - Campaign | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 138.62 |  | 0 | 1062 |  | 0 | 2749 |  | 0 | 841 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4790.62
1 | 5 | 1 | 9 | GSO | Legal | LT | 9870% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Legal | LT | 98.7 |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Legal | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 5 | 1 | 9 | GSO | Estimating | LT | 6100% |  | 0 | 4880 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4880 |  | 4880 |  |  | Estimating | LT | 61 |  | 0 | 4880 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4880 |  |  | Estimating | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 5 | 1 | 4 | GSO | Siting - Chapter 40A | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 5355 |  | 0 | 5788 |  | 0 | 11360 |  | 0 | 2780 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 25283 |  | 25283 |  |  | Siting - Chapter 40A | LT |  |  | 0 |  |  |  | 0 |  | 0 | 5100 |  | 0 | 5300 |  | 0 | 10100 |  | 0 | 2400 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 22900 | as per Estimate request 7/28/23 |  | Veg. Mgmt | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 255 |  | 0 | 488 |  | 0 | 1260 |  | 0 | 380 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2383
1 | 5 | 1 | 9 | GSO | Asset Management | LT |  |  | 0 | 0 |  | 0 | 0 |  | 40 | 2407 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 40 | 2407 |  | 2407 |  |  | Asset Management | LT | 57.3 |  | 0 |  |  |  | 0 |  | 40 | 2292 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 40 | 2292 |  |  | Other - | LT |  |  |  | 0 |  |  | 0 |  |  | 115 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 115
1 | 5 | 1 | 9 | GSO | Veg. Mgmt | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Veg. Mgmt | LT | 61.5 |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Other - | LT |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
1 | 5 | 1 | 9 | GSO | Other - | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other - | LT | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | [10 empty] | 0 | [28 empty] | 0 | 0
1 | 5 | 1 | 9 | GSO | Other - | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other - | LT | 0 |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | LT Total | LT |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
1 | 5 | 1 | 9 | GSO | Other - | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Other - | LT | 0 |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Other - | LT |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | LT Total |  | 0% |  |  | 72230.2 |  | 136 | 14946 |  | 520 | 100714 |  | 521.6 | 136428 |  | 1366.4 | 167766 |  | 984 | 81540 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 3528 | 573624.2 |  | 573624.2 |  |  | LT Total |  |  |  |  | 72230.2 |  | 136 | 14945.95 |  | 520 | 95917.38 |  | 521.6 | 124934 |  | 1366.4 | 149157.47 |  | 984 | 70384 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 3528 | 527569 |  |  | LT Total |  |  |  |  | 0 |  | 0 | 0.05 |  | 0 | 4796.62 |  | 0 | 11494 |  | 0 | 18608.53 |  | 0 | 11156 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 46055.2
5 | 5 | 6 | 9 |  | Employee Expenses | AE | 5% |  | 0 | 0 |  |  | 747 |  | 0 | 5036 |  | 0 | 6822 |  | 0 | 8388 |  | 0 | 4077 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 25070 |  | 25070 |  |  | Employee Expenses | AE | 5% |  | 0 | 0 |  |  | 747 |  | 0 | 4796 |  | 0 | 6247 |  | 0 | 7458 |  | 0 | 3519 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 22767 |  |  | Employee Expenses | AE |  |  |  | 0 |  |  | 0 |  | 0 | 240 |  | 0 | 575 |  | 0 | 930 |  | 0 | 558 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2303
3 | 5 | 3 | 9 | OS | Project Support Vendor - PM | AQ | 16000% |  | 0 | 15427.62 |  | 0 | 0 |  | 120 | 3961 |  | 560 | 97843 |  | 2040 | 367122 |  | 1640 | 303991 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 4360 | 788344.62 |  | 788344.62 |  |  | Project Support Vendor - PM | AQ | 160 |  | 0 | 15427.62 |  | 0 | 0 |  | 120 | 3772.38 |  | 560 | 89600 |  | 2040 | 326400 |  | 1640 | 262400 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 4360 | 697600 | asst pm and external suppport |  | Project Support Vendor - PM | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 188.62 |  | 0 | 8243 |  | 0 | 40722 |  | 0 | 41591 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 90744.62
3 | 5 | 3 | 9 | OS | Project Support Vendor - IP | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - IP | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - IP | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - C/P | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - C/P | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - C/P | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - System Planning | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - System Planning | AQ | 160 |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - System Planning | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
3 | 5 | 3 | 2 | OS | Project Support Vendor - Enviromental | AQ | 0% |  | 0 | 0 |  | 11.2 | 1873 |  | 56 | 9831 |  | 73.92 | 13496 |  | 0 | 15587 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 141.12 | 40787 |  | 40787 |  |  | Project Support Vendor - Enviromental | AQ | 0% |  | 0 |  |  | 11.2 | 1873 |  | 56 | 9363 |  | 73.92 | 12359 |  | 0 | 13858 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 141.12 | 37453 |  |  | Project Support Vendor - Enviromental | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 468 |  | 0 | 1137 |  | 0 | 1729 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3334
3 | 5 | 3 | 3 | OS | Project Support Vendor - SCS - Campaign | AQ | 0% |  | 0 | 2632.5 |  | 0 | 0 |  | 0 | 43887 |  | 0 | 50429 |  | 0 | 99136 |  | 0 | 24572 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 220656.5 |  | 220656.5 |  |  | Project Support Vendor - SCS - Campaign | AQ | 0% |  | 0 | 2632.5 |  | 0 | 0 | False) | 0 | 41797.5 |  | 0 | 46180 |  | 0 | 88140 |  | 0 | 21210 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 199960 |  |  | Project Support Vendor - SCS - Campaign | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 2089.5 |  | 0 | 4249 |  | 0 | 10996 |  | 0 | 3362 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20696.5
3 | 5 | 3 | 9 | OS | Project Support Vendor - Legal | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Legal | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Legal | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - Estimating | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Estimating | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Estimating | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 4 | OS | Project Support Vendor - Siting - Chapter 40A | AQ | 0% |  | 0 | 10307 |  | 0 | 0 |  | 0 | 37268 |  | 0 | 51979 |  | 0 | 102241 |  | 0 | 25371 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 227166 |  | 227166 |  |  | Project Support Vendor - Siting - Chapter 40A | AQ | 0% |  | 0 | 10307 |  | 0 | 0 |  | 0 | 35493 |  | 0 | 47600 |  | 0 | 90900 |  | 0 | 21900 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 206200 |  |  | Project Support Vendor - Siting - Chapter 40A | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 1775 |  | 0 | 4379 |  | 0 | 11341 |  | 0 | 3471 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20966
3 | 5 | 3 | 9 | OS | Project Support Vendor - Asset Management | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Asset Management | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Asset Management | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - Veg. Mgmt. | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Veg. Mgmt. | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Veg. Mgmt. | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - Other | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Other | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Other | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - Other | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Other | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Other | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 5 | 3 | 9 | OS | Project Support Vendor - Other | AQ | 16000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Project Support Vendor - Other | AQ | 160 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Project Support Vendor - Other | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 5 | 6 | 9 |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Vehicles ( now in indirects section) | AV |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 5 | 6 | 11 |  | Property or CWIP tax large proj. allowance | BR | 0% |  | 0 | 3582.77 |  |  | 4217 |  | 0 | 110355 |  | 0 | 260005 |  | 0 | 561368 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 939527.77 |  | 939527.77 |  |  | Property or CWIP tax large proj. allowance | BR |  |  | 0 | 3582.77 |  |  | 4217.23 |  | 0 | 105100 |  |  | 238100 |  | 0 | 499100 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 850100 |  |  | Property or CWIP tax large proj. allowance | BR |  |  |  | 0 |  |  | -0.23 |  | 0 | 5255 |  | 0 | 21905 |  | 0 | 62268 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 89427.77
5 | 5 | 6 | 11 |  | Builder All risk insurance excluding deductables( if project is over $50m) | BR | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Builder All risk insurance excluding deductables( if project is over $50m) | BR | 0% |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Builder All risk insurance excluding deductables( if project is over $50m) | BR |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 5 | 6 | 2 |  | Fees and Payments - Enviromental | BF | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Fees and Payments - Enviromental | BF |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Fees and Payments - Enviromental | BF |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 5 | 6 | 4 |  | Fees and Payments - Siting | BF | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Fees and Payments - Siting | BF |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Fees and Payments - Siting | BF |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 5 | 6 | 9 |  | Fees and Payments - Other | BF | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Fees and Payments - Other | BF |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Fees and Payments - Other | BF |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | PSMXX Subtotal |  | 0% |  | 0 | 104180.09 |  | 147.2 | 21783 |  | 696 | 311052 |  | 1155.52 | 617002 |  | 3406.4 | 1321608 |  | 2624 | 439551 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 2815176.09 |  | 2815176.09 |  |  | PSMXX Subtotal |  |  |  |  | 104180.09 |  |  | 21783.18 |  |  | 296239.26 |  |  | 565020 |  |  | 1175013.47 |  |  | 379413 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2541649 |  |  | PSMXX Subtotal |  |  |  |  | 0 |  |  | -0.18 |  |  | 14812.74 |  |  | 51982 |  |  | 146594.53 |  |  | 60138 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 273527.09
| 9 |  | 99 |  | Escalation |  | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Escalation |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 8 | 6 | 11 |  | journal entry adj | P1 | 0% |  | 0 | -4620 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | -4620 |  | -4620 |  |  | journal entry adj |  | 0% |  | 0 | -4620 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | -4620 |  |  | journal entry adj | P1 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | PSMXX Total |  | 0% |  | 0 | 99560.09 |  | 147.2 | 21783 |  | 696 | 311052 |  | 1155.52 | 617002 |  | 3406.4 | 1321608 |  | 2624 | 439551 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 8029.12 | 2810556.09 |  | 2810556.09 |  |  | PSMXX Total |  |  |  |  | 99560.09 |  | 147.2 | 21783.18 |  | 696 | 296239.26 |  | 1155.52 | 565020 |  | 3406.4 | 1175013.47 |  | 2624 | 379413 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 8029.12 | 2537029 |  |  | PSMXX Total |  |  |  | 0 | 0 |  | 0 | -0.18 |  | 0 | 14812.74 |  | 0 | 51982 |  | 0 | 146594.53 |  | 0 | 60138 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 273527.09
[5 empty] | REMXX-TG REMOVAL |  | 0% | [34 empty] | 0 | 0 |  | 0 |  |  | REMXX-TG REMOVAL | [36 empty] | 0 | 0 |  |  | REMXX-TG REMOVAL | [36 empty] | 0 | 0
1 | 6 | 5 | 10 | E&S | Engineering/Design | LT | 5730% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Engineering/Design | LT | 57.3 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Engineering/Design | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 6 | 5 | 10 | E&S | Internal Construction | LT | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Internal Construction | LT |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Internal Construction | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | LT Total |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | LT Total |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | LT Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
5 | 6 | 5 | 10 |  | Employee Expenses | AE | 15% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | Employee Expenses | AE | 15% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Employee Expenses | AE |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 6 | 5 | 10 | OS | Outside Services | AO | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Outside Services | AO | 0% |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Outside Services | AO |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 6 | 5 | 10 | OS | Contractor Labor | AQ | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Contractor Labor | AQ | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Contractor Labor | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 6 | 5 | 10 |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Vehicles ( now in indirects section) | AV |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 6 | 5 | 10 |  | Rents and Leases | BR | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Rents and Leases | BR |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Rents and Leases | BR |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | REMXX Subtotal |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | REMXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | REMXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0
| 9 |  | 99 |  | Escalation |  | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Escalation |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 8 | 6 | 11 |  | 0 | P1 | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 | P1 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | REMXX Total |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | REMXX Total |  |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | REMXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | TSTXX-TG TEST |  | 0% | [34 empty] | 0 | 0 |  | 0 |  |  | TSTXX-TG TEST | [36 empty] | 0 | 0 |  |  | TSTXX-TG TEST | [36 empty] | 0 | 0
1 | 7 | 1 | 8 | E&S | Test / Field Engr. Labor (In House) | LT | 6400% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Test / Field Engr. Labor (In House) | LT | 64 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Test / Field Engr. Labor (In House) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 7 | 1 | 8 | E&S | Test / Comm. Engr. Labor (In House) | LT | 5200% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Test / Comm. Engr. Labor (In House) | LT | 52 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Test / Comm. Engr. Labor (In House) | LT |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
3 | 7 | 3 | 8 | E&S | Lead Commissioning Engr. (LCE) ( internal) | AQ | 6400% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Lead Commissioning Engr. (LCE) ( internal) | LT | 64 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Lead Commissioning Engr. (LCE) ( internal) | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 7 | 6 | 8 |  | Employee Expense | AE | 10% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | Employee Expense | AE | 10% |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Employee Expense | AE |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
3 | 7 | 3 | 8 | OS | Test / Field Engr. Labor (contractor) | AQ | 19100% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1000 | 214829 |  | 2200 | 486803 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 3200 | 701632 |  | 701632 |  |  | Test / Field Engr. Labor (contractor) | AQ | 191 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1000 | 191000 |  | 2200 | 420200 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 3200 | 611200 | Eversource testing and commisioning of system |  | Test / Field Engr. Labor (contractor) | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 23829 |  | 0 | 66603 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 90432
3 | 7 | 3 | 8 | OS | Test / Comm. Engr. Labor (contractor) | AQ | 19100% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 450 | 96673 |  | 1200 | 265529 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1650 | 362202 |  | 362202 |  |  | Test / Comm. Engr. Labor (contractor) | AQ | 191 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 450 | 85950 |  | 1200 | 229200 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1650 | 315150 | As per P&C and PMT |  | Test / Comm. Engr. Labor (contractor) | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10723 |  | 0 | 36329 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 47052
3 | 7 | 3 | 8 | OS | Lead Commissioning Engr. (LCE) (contactor) | AQ | 22000% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Lead Commissioning Engr. (LCE) (contactor) | AQ | 220 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Lead Commissioning Engr. (LCE) (contactor) | AQ |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 7 | 6 | 8 |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Vehicles ( now in indirects section) | AV | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | Vehicles ( now in indirects section) | AV |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | TSTXX Subtotal |  | 0% |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 311502 |  |  | 752332 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1063834 |  | 1063834 |  |  | TSTXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 276950 |  |  | 649400 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 926350 |  |  | TSTXX Subtotal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 34552 |  |  | 102932 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 137484
| 9 |  | 99 |  | Escalation |  | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | Escalation |  |  |  | 0 | 0 | [31 empty] | 0 | 0 |  |  | Escalation |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
5 | 8 | 6 | 11 |  | 0 | P1 | 0% |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 | P1 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | TSTXX Total |  | 0% |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1450 | 311502 |  | 3400 | 752332 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 4850 | 1063834 |  | 1063834 |  |  | TSTXX Total |  |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1450 | 276950 |  | 3400 | 649400 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 4850 | 926350 |  |  | TSTXX Total |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 34552 |  | 0 | 102932 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 137484
[5 empty] | SUBTOTAL PROJECT DIRECT COST |  | 0% |  | 0 | 136816.64 |  | 147.2 | 21783 |  | 3096 | 5084192.3037 |  | 3835.52 | 5686143.5387 |  | 28416.7473 | 11418688.2391 |  | 14363.4491 | 2999493.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 49858.9163 | 25347117.6928 |  | 25347117.6928 |  |  | SUBTOTAL PROJECT DIRECT COST |  |  |  | 0 | 136816.64 |  | 147.2 | 21783.18 |  |  | 4923951.75 |  | 3835.52 | 5375936.42 |  | 28416.7473 | 10356366.26 |  | 14363.4491 | 2589111 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 49858.9163 | 23403965.25 |  |  | SUBTOTAL PROJECT DIRECT COST |  |  |  | 0 | 0 |  | 0 | -0.18 |  | 0 | 160240.5537 |  | 0 | 310207.1187 |  | 0 | 1062321.9791 |  | 0 | 410382.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1943152.4428
[7 empty] | 0% | [34 empty] | 0 | 0 |  | 0 | [39 empty] | 0 | 0 | [39 empty] | 0 | 0
[5 empty] | Risk | [39 empty] | 0 |  |  | Risk | [40 empty] | Risk
5 | 8 | 6 | 12 |  | Risk |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 900000 |  | 0 | 1650000 |  | 0 | 1400000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3950000 |  | 3950000 |  |  | Risk | [7 empty] | 0 |  |  | 0 |  |  | 900000 |  |  | 1650000 |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 3950000 | no escalation added |  | Risk | [36 empty] | 0 | 0
5 | 8 | 6 | 12 |  | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [9 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | no escalation added |  | 0 | [36 empty] | 0 | 0
5 | 8 | 6 | 12 | [5 empty] | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [9 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [39 empty] | 0 | 0
[5 empty] | Risk Total |  | 0% |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 900000 |  |  | 1650000 |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3950000 |  | 3950000 |  |  | Risk Total |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 900000 |  |  | 1650000 |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3950000 |  |  | Risk Total |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | TOTAL PROJECT DIRECT COST |  | 0% |  | 0 | 136816.64 |  | 147.2 | 21783 |  | 3096 | 5084192.3037 |  | 3835.52 | 6586143.5387 |  | 28416.7473 | 13068688.2391 |  | 14363.4491 | 4399493.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 49858.9163 | 29297117.6928 |  | 29297117.6928 |  |  | TOTAL PROJECT DIRECT COST (w risk) |  |  |  | 0 | 136816.64 |  | 147.2 | 21783.18 |  | 0 | 4923951.75 |  | 3835.52 | 6275936.42 |  | 28416.7473 | 12006366.26 |  | 14363.4491 | 3989111 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 49858.9163 | 27353965.25 |  |  | TOTAL PROJECT DIRECT COST |  |  |  | 0 | 0 |  | 0 | -0.18 |  | 0 | 160240.5537 |  | 0 | 310207.1187 |  | 0 | 1062321.9791 |  | 0 | 410382.9713 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1943152.4428
0
[5 empty] | INDIRECTS |  | 0% | [37 empty] | 0 |  |  | INDIRECTS | [40 empty] | INDIRECTS
6 | 10 | 7 | 13 |  | Non-Productive Time Allocation (ZNP) | 58 | 19% |  | 0 | 16810.89 |  |  | 2840 |  | 0 | 25654 |  | 0 | 18025 |  | 0 | 36100 |  | 0 | 23463 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 122892.89 |  | 122892.89 |  |  | Non-Productive Time Allocation (ZNP) |  | 19% |  | 0 | 16810.89 |  |  | 2840 |  |  | 24432 |  |  | 16506.11 |  |  | 32096 |  |  | 20253 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 112938 |  |  | Non-Productive Time Allocation (ZNP) |  |  |  |  | 0 |  |  | 0 |  | 0 | 1222 |  | 0 | 1518.89 |  | 0 | 4004 |  | 0 | 3210 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 9954.89
6 | 10 | 7 | 13 |  | Payroll Benefits Allocation (ZPB) incl NPT | 59 | 8% |  | 0 | 4.81 |  |  | 0 |  | 0 | 3260 |  | 0 | 5242 |  | 0 | 2117 |  | 0 | 3993 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 14616.81 |  | 14616.81 |  |  | Payroll Benefits Allocation (ZPB) incl NPT |  | 8% |  | 0 | 4.81 |  |  | 0 |  |  | 3105.19 |  |  | 4800 |  |  | 1882 |  |  | 3447 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13239 |  |  | Payroll Benefits Allocation (ZPB) incl NPT | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 154.81 |  | 0 | 442 |  | 0 | 235 |  | 0 | 546 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 1377.81
6 | 10 | 7 | 13 |  | Gen SVC CO Overhead (ZGS) incl NPT | 60 | 70% |  | 0 | 79696.06 |  |  | 12450 |  | 0 | 83894 |  | 0 | 26616 |  | 0 | 139749 |  | 0 | 67923 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 410328.06 |  | 410328.06 |  |  | Gen SVC CO Overhead (ZGS) incl NPT |  | 70% |  | 0 | 79696.06 |  |  | 12450 |  |  | 79899 |  |  | 24373.94 |  |  | 124248 |  |  | 58630 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 379297 |  |  | Gen SVC CO Overhead (ZGS) incl NPT | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 3995 |  | 0 | 2242.06 |  | 0 | 15501 |  | 0 | 9293 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 31031.06
6 | 10 | 7 | 13 |  | E&S Allocations (ZEB,ZEL,ZES) | 61 | 65% |  | 0 | 95961.95 |  |  | 20871 |  | 0 | 313610 |  | 0 | 511886 |  | 0 | 4140422 |  | 0 | 2002349 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 7085099.95 |  | 7085099.95 |  |  | E&S Allocations (ZEB,ZEL,ZES) |  | 65% |  | 0 | 95961.95 |  |  | 20871 |  |  | 298676.05 |  |  | 468760 |  |  | 3681160 |  |  | 1728394 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6293823 |  |  | E&S Allocations (ZEB,ZEL,ZES) | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 14933.95 |  | 0 | 43126 |  | 0 | 459262 |  | 0 | 273955 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 791276.95
6 | 10 | 7 | 13 |  | AS&E Allocations (ZAS) | 62 | 0.9% |  | 0 | 2925.42 |  |  | 521 |  | 0 | 47298 |  | 0 | 57890 |  | 0 | 143702 |  | 0 | 45876 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 298212.42 |  | 298212.42 |  |  | AS&E Allocations (ZAS) |  | 0.9% |  | 0 | 2925.42 |  |  | 521 |  |  | 45045.58 |  |  | 53013 |  |  | 127762 |  |  | 39599 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 268866 |  |  | AS&E Allocations (ZAS) | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 2252.42 |  | 0 | 4877 |  | 0 | 15940 |  | 0 | 6277 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 29346.42
6 | 10 | 7 | 13 |  | Stores Expense Allocation (ZST) | 62 | 5% |  | 0 | 0 |  |  | 0 |  | 0 | 226786 |  | 0 | 243137 |  | 0 | 243066 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 712989 |  | 712989 |  |  | Stores Expense Allocation (ZST) |  | 5% |  | 0 | 0 |  |  | 0 |  |  | 215987 |  |  | 222653 |  |  | 216105 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 654745 |  |  | Stores Expense Allocation (ZST) | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 10799 |  | 0 | 20484 |  | 0 | 26961 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 58244
6 | 10 | 7 | 13 |  | Lobby Stock |  | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | Lobby Stock |  | 0% |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Lobby Stock | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
6 | 10 | 7 | 13 |  | MDEC (ZMI) |  | 7% |  | 0 | 12844.6 |  |  | 1376 |  | 0 | 25266 |  | 0 | 53263 |  | 0 | 436109 |  | 0 | 210883 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 739741.6 |  | 739741.6 |  |  | MDEC (ZMI) |  | 7% |  | 0 | 12844.6 |  |  | 1376 |  |  | 24062.4 |  |  | 48776 |  |  | 387735 |  |  | 182031 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 656825 |  |  | MDEC (ZMI) | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 1203.6 |  | 0 | 4487 |  | 0 | 48374 |  | 0 | 28852 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 82916.6
6 | 10 | 7 | 13 |  | Vehicles (ZVE) |  | 21.18% |  | 0 | 837.08 |  |  | 2329 |  | 0 | 28597 |  | 0 | 40556 |  | 0 | 40242 |  | 0 | 26156 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 138717.08 |  | 138717.08 |  |  | Vehicles (ZVE) |  | 21.18% |  | 0 | 837.08 |  |  | 2328.92 |  |  | 27235 |  |  | 37139 |  |  | 35778 |  |  | 22577 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 125895 |  |  | Vehicles (ZVE) | 0 |  |  |  | 0 |  |  | 0.08 |  | 0 | 1362 |  | 0 | 3417 |  | 0 | 4464 |  | 0 | 3579 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 12822.08
7 | 11 | 7 | 13 |  | 0 | 63 | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  |  |  | 0% |  | 0 | 0 |  |  |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
[5 empty] | Indirects Subtotal |  | 0% |  |  | 209080.81 |  |  | 40387 |  |  | 754365 |  |  | 956615 |  |  | 5181507 |  |  | 2380643 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 9522597.81 |  | 9522597.81 |  |  | Indirects Subtotal |  |  |  |  | 209080.81 |  |  | 40386.92 |  |  | 718442.22 |  |  | 876021.05 |  |  | 4606766 |  |  | 2054931 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 8505628 |  |  | Indirects Subtotal |  |  |  |  | 0 |  |  | 0.08 |  |  | 35922.78 |  |  | 80593.95 |  |  | 574741 |  |  | 325712 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 1016969.81
[5 empty] | TOTAL PROJECT COST - Direct & Indirect ( excl AFUDC ) |  |  |  |  | 345897.45 |  |  | 62170 |  |  | 5838557.3037 |  |  | 7542758.5387 |  |  | 18250195.2391 |  |  | 6780136.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 38819715.5028 |  | 38819715.5028 |  |  | TOTAL PROJECT COST - Direct & Indirect ( excl AFUDC ) |  |  |  |  | 345897.45 |  |  | 62170.1 |  |  | 5642393.97 |  |  | 7151957.47 |  |  | 16613132.26 |  |  | 6044042 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 35859593.25 |  |  | TOTAL PROJECT COST - Direct & Indirect ( excl AFUDC ) |  |  |  |  | 0 |  |  | -0.1 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2960122.2528
[5 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [43 empty] | 0 | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | AFUDC |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | AFUDC | [37 empty] | 0 |  |  | AFUDC |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
7 | 11 | 8 | 14 |  | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | [40 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
7 | 11 | 8 | 14 |  | AFUDC (ZK) |  |  |  | 0 | 25374.34 |  | 0.07 | 2791 |  | 0.07 | 228093 |  | 0.07 | 723923 |  | 0.07 | 1660900 |  | 0.07 | 657500 |  | 0.07 | 0 |  | 0.07 | 0 |  | 0.07 | 0 |  | 0.07 | 0 |  | 0.07 | 0 |  | 0.7 | 3298581.34 |  | 3298581.34 |  |  | AFUDC (ZK) |  |  |  |  | 25374.34 |  | 7% | 2790.66 |  | 7% | 228093 |  | 7% | 723923 |  | 7% | 1660900 |  | 7% | 657500 |  | 7% | 0 |  | 7% | 0 |  | 7% | 0 |  | 7% | 0 |  | 7% | 0 |  | 0.7 | 3298581 |  |  | AFUDC (ZK) |  |  |  |  | 0 |  |  | 0.34 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.34
[5 empty] | In Service Dollars / Land costs | [36 empty] | 0 | 0 |  |  |  |  | In Service Dollars / Land costs | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | [39 empty] | 0 | 0
7 | 11 | 8 | 14 |  | Cumulative IS$ & Land Costs |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Cumulative IS$ & Land Costs | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | Cumulative IS$ & Land Costs |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
7 | 11 | 8 | 14 |  | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [39 empty] | 0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | AFUDC Subtotal |  |  |  |  | 25374.34 |  |  | 2791 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581.34 | 0 | 3298581.34 | 0 |  | AFUDC Subtotal |  |  |  |  | 25374.34 |  |  | 2790.66 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581 |  |  | AFUDC Subtotal |  |  |  |  | 0 |  |  | 0.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.34
[45 empty] | 0 | [43 empty] | 0
[45 empty] | 0 | [43 empty] | 0
[5 empty] | TOTAL PROJECT COST - Baseline Budget |  |  |  |  | 371271.79 |  |  | 64961 |  |  | 6066650.3037 |  |  | 8266681.5387 |  |  | 19911095.2391 |  |  | 7437636.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 42118296.8428 | 0 | 42118296.8428 | 0 |  | TOTAL PROJECT COST - Baseline Budget |  |  |  |  | 371271.79 |  |  | 64960.76 |  |  | 5870486.97 |  |  | 7875880.47 |  |  | 18274032.26 |  |  | 6701542 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 39158174.25 |  |  | TOTAL PROJECT COST - Baseline Budget |  |  |  |  | 0 |  |  | 0.24 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2960122.5928
[5 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [43 empty] | 0
[5 empty] | Contingecy |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | Contingecy | [37 empty] | 0 |  |  | Contingecy |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
5 | 8 | 6 | 15 |  | Contingency |  |  |  | 0 | 0 |  |  | 1046 |  | 0 | 458006.1266 |  | 0 | 481997.312 |  | 0 | 747976.7619 |  | 0 | 118859.37 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 1807885.5705 |  | 1807885.5705 |  |  | Contingency |  |  |  |  | 0 |  |  | 1046.1175 |  |  | 458006.1266 |  |  | 481997.312 |  |  | 747976.7619 |  |  | 118859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1807885.688 |  |  | Contingency |  |  |  |  | 0 |  |  | -0.1175 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | -0.1175
5 | 8 | 6 | 15 |  | Other |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | Other |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Other |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
5 | 8 | 6 | 15 |  | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | [40 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
[5 empty] | Contingency SubTotal |  |  |  |  | 0 |  |  | 1046 |  |  | 458006.1266 |  |  | 481997.312 |  |  | 747976.7619 |  |  | 118859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1807885.5705 |  | 1807885.5705 |  |  | Contingency SubTotal |  |  |  |  | 0 |  |  | 1046.1175 |  |  | 458006.1266 |  |  | 481997.312 |  |  | 747976.7619 |  |  | 118859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1807885.688 |  |  | Contingency SubTotal |  |  |  |  | 0 |  |  | -0.1175 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -0.1175
[5 empty] | 0 | [39 empty] | 0 | [43 empty] | 0
[5 empty] | TOTAL PROJECT COST - Approved Funding |  |  |  | 0 | 371271.79 |  |  | 66007 |  | 0 | 6524656.4303 |  | 0 | 8748678.8507 |  | 0 | 20659072.001 |  | 0 | 7556496.3413 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 43926182.4133 |  | 43926182.4133 |  |  | TOTAL PROJECT COST - Approved Funding |  |  |  |  | 371271.79 |  |  | 66006.8775 |  |  | 6328493.0966 |  |  | 8357877.782 |  |  | 19022009.0219 |  |  | 6820401.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 40966059.938 |  |  | TOTAL PROJECT COST - Approved Funding |  |  |  |  | 0 |  |  | 0.1225 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2960122.4753
[5 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [43 empty] | 0
8 | 12 | 16 | 16 |  | Reimbursables / Customer Contribution |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | Reimbursables / Customer Contribution | [37 empty] | 0 |  |  | Reimbursables / Customer Contribution |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
8 | 12 | 16 | 16 |  | Reimbursables / Customer Contribution ( enter as negative) |  |  |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | Reimbursables / Customer Contribution ( enter as negative) |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Reimbursables / Customer Contribution ( enter as negative) |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
8 | 12 | 16 | 16 |  | 0 | 59 | 0% |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 0% |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
[5 empty] | TOTAL PROJECT COST |  |  |  |  | 371271.79 |  |  | 66007 |  |  | 6524656.4303 |  |  | 8748678.8507 |  |  | 20659072.001 |  |  | 7556496.3413 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 43926182.4133 | 0 | 43926182.4133 |  |  | TOTAL PROJECT COST |  |  |  |  | 371271.79 |  |  | 66006.8775 |  |  | 6328493.0966 |  |  | 8357877.782 |  |  | 19022009.0219 |  |  | 6820401.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 40966059.938 |  |  | TOTAL PROJECT COST |  |  |  |  | 0 |  |  | 0.1225 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 2960122.4753 | 43926182.4133
[13 empty] | 66000 |  |  | 6524500 |  |  | 8748600 |  |  | 20659000 |  |  | 7556500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 43554600
[13 empty] | -7 |  |  | -156.4303 |  |  | -78.8507 |  |  | -72.001 |  |  | 3.6587 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | Check | 43926182.4133
-371582.4133
Total Escalation
[48 empty] | Total Contingency | P1
[9 empty] | Prior actuals to date |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  |  | 2029-01-01 |  |  | 2030-01-01 |  |  | 2031-01-01 |  |  | 2032-01-01 |  |  | 2033-01-01 |  |  | TOTAL | [9 empty] | Prior |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  |  | 2029-01-01 |  |  | 2030-01-01 |  |  | 2031-01-01 |  |  | 2032-01-01 |  |  | 2033-01-01 |  |  | TOTAL | [7 empty] | Prior |  |  | 45292 |  |  | 45658 |  |  | 46023 |  |  | 46388 |  |  | 46753 |  |  | 47119 |  |  | 47484 |  |  | 47849 |  |  | 48214 |  |  | 48580 |  |  | TOTAL
|  |  | Summary by WBS | [5 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS
|  |  | 1 |  | ROW / Easements / Land purchases |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | ROW / Easements / Land purchases |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | ROW / Easements / Land purchases |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 2 |  | Environmental Approvals / Permits |  |  |  |  | 5060.05 |  |  | 9175 |  |  | 74732 |  |  | 102591 |  |  | 118479 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 310037.05 |  |  |  |  | Environmental Approvals / Permits |  |  |  |  | 5060.05 |  |  | 9174.95 |  |  | 71173 |  |  | 93948 |  |  | 105337 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 284693 |  |  | Environmental Approvals / Permits |  |  |  |  | 0 |  |  | 0.05 |  |  | 3559 |  |  | 8643 |  |  | 13142 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 25344.05
|  |  | 3 |  | Outreach |  |  |  |  | 10968.12 |  | ` | 0 |  |  | 46797 |  |  | 63037 |  |  | 123920 |  |  | 30716 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 275438.12 |  |  |  |  | Outreach |  |  |  |  | 10968.12 |  |  | 0 |  |  | 44568.88 |  |  | 57726 |  |  | 110175 |  |  | 26513 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 249951 |  |  | Outreach |  |  |  |  | 0 |  |  | 0 |  |  | 2228.12 |  |  | 5311 |  |  | 13745 |  |  | 4203 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 25487.12
|  |  | 4 |  | Siting Approvals / Permits |  |  |  |  | 10307 |  |  | 0 |  |  | 42623 |  |  | 57767 |  |  | 113601 |  |  | 28151 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 252449 |  |  |  |  | Siting Approvals / Permits |  |  |  |  | 10307 |  |  | 0 |  |  | 40593 |  |  | 52900 |  |  | 101000 |  |  | 24300 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 229100 |  |  | Siting Approvals / Permits |  |  |  |  | 0 |  |  | 0 |  |  | 2030 |  |  | 4867 |  |  | 12601 |  |  | 3851 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 23349
|  |  | 5 |  | Engineering / Design |  |  |  |  | 16424.06 |  |  | 0 |  |  | 330740 |  |  | 390211 |  |  | 17431 |  |  | 34890 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 789696.06 |  |  |  |  | Engineering / Design |  |  |  |  | 16424.06 |  |  | 0 |  |  | 314989.94 |  |  | 357337 |  |  | 15498 |  |  | 30116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 734365 |  |  | Engineering / Design |  |  |  |  | 0 |  |  | 0 |  |  | 15750.06 |  |  | 32874 |  |  | 1933 |  |  | 4774 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 55331.06
|  |  | 6 |  | Materials ( Eversource purchased) |  |  |  |  | 2358 |  |  | 0 |  |  | 4449401.6937 |  |  | 4678394.7327 |  |  | 4631610.7853 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13761765.2117 |  |  |  |  | Materials ( Eversource purchased) |  |  |  |  | 2358 |  |  | 0 |  |  | 4319738.79 |  |  | 4453069.42 |  |  | 4322096.79 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13097263 |  |  | Materials ( Eversource purchased) |  |  |  |  | 0 |  |  | 0 |  |  | 129662.9037 |  |  | 225325.3127 |  |  | 309513.9953 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 664502.2117
|  |  | 7 |  | Construction ( incl materials by contractors) |  |  |  |  | 10963.25 |  |  | 0 |  |  | 509.85 |  |  | 535.806 |  |  | 5136536.4538 |  |  | 1772720.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6921266.3311 |  |  |  |  | Construction ( incl materials by contractors) |  |  |  |  | 10963.25 |  |  | 0 |  |  | 495 |  |  | 510 |  |  | 4566808 |  |  | 1530182 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6108958.25 |  |  | Construction ( incl materials by contractors) |  |  |  |  | 0 |  |  | 0 |  |  | 14.85 |  |  | 25.806 |  |  | 569728.4538 |  |  | 242538.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 812308.0811
|  |  | 8 |  | Testing / Commissioning |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 311502 |  |  | 752332 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1063834 |  |  |  |  | Testing / Commissioning |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 276950 |  |  | 649400 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 926350 |  |  | Testing / Commissioning |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 34552 |  |  | 102932 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 137484
|  |  | 9 |  | PMT Project Mgmt Team |  |  |  |  | 74262.15 |  |  | 8391 |  |  | 36545 |  |  | 133602 |  |  | 404240 |  |  | 380684 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1037724.15 |  |  |  |  | PMT Project Mgmt Team |  |  |  |  | 74262.15 |  |  | 8391 |  |  | 34804.38 |  |  | 122346 |  |  | 359401.47 |  |  | 328600 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 927805 |  |  | PMT Project Mgmt Team |  |  |  |  | 0 |  |  | 0 |  |  | 1740.62 |  |  | 11256 |  |  | 44838.53 |  |  | 52084 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 109919.15
|  |  | 10 |  | Removals |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Removals |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Removals |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 11 |  | Other ( property taxes and BAR) |  |  |  |  | 6474.01 |  |  | 4217 |  |  | 102843.76 |  |  | 260005 |  |  | 561368 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 934907.77 |  |  |  |  | Other ( property taxes and BAR) |  |  |  |  | 6474.01 |  |  | 4217.23 |  |  | 97588.76 |  |  | 238100 |  |  | 499100 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 845480 |  |  | Other ( property taxes and BAR) |  |  |  |  | 0 |  |  | -0.23 |  |  | 5255 |  |  | 21905 |  |  | 62268 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 89427.77
|  |  | 12 |  | Risks |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 900000 |  |  | 1650000 |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3950000 |  |  |  |  | Risks |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 900000 |  |  | 1650000 |  |  | 1400000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3950000 |  |  | Risks |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 13 |  | Indirects/Overhead |  |  |  |  | 209080.81 |  |  | 40387 |  |  | 754365 |  |  | 956615 |  |  | 5181507 |  |  | 2380643 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9522597.81 |  |  |  |  | Indirects/Overhead |  |  |  |  | 209080.81 |  |  | 40386.92 |  |  | 718442.22 |  |  | 876021.05 |  |  | 4606766 |  |  | 2054931 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 8505628 |  |  | Indirects/Overhead |  |  |  |  | 0 |  |  | 0.08 |  |  | 35922.78 |  |  | 80593.95 |  |  | 574741 |  |  | 325712 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1016969.81
|  |  | 14 |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2791 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581.34 |  |  |  |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2790.66 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581 |  |  | AFUDC |  |  |  |  | 0 |  |  | 0.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.34
|  |  | 15 |  | Contingency |  |  |  |  | 0 |  |  | 1046 |  |  | 458006.1266 |  |  | 481997.312 |  |  | 747976.7619 |  |  | 118859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1807885.5705 |  |  |  |  | Contingency |  |  |  |  | 0 |  |  | 1046.1175 |  |  | 458006.1266 |  |  | 481997.312 |  |  | 747976.7619 |  |  | 118859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1807885.688 |  |  | Contingency |  |  |  |  | 0 |  |  | -0.1175 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -0.1175
|  |  | 16 |  | Reimbursables/Customer Contribution |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Reimbursables/Customer Contribution |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Reimbursables/Customer Contribution |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 17 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 18 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 19 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 20 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 21 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 22 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 23 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 24 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 25 |  | O&M / Expense |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | O&M / Expense |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | O&M / Expense |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 26 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 27 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 28 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 29 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 30 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 31 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 32 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 33 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 34 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 35 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 36 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 37 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 38 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 39 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 40 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 41 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 42 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 43 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 44 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 45 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 46 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 47 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 48 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 49 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 50 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 51 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 52 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 53 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 54 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 55 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 56 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 57 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 58 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 59 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 60 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 61 |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | NA |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Total costs by WBS |  |  |  |  | 371271.79 |  |  | 66007 |  |  | 6524656.4303 |  |  | 8748678.8507 |  |  | 20659072.001 |  |  | 7556496.3413 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 43926182.4133 |  |  |  |  | Total costs by WBS |  |  |  |  | 371271.79 |  |  | 66006.8775 |  |  | 6328493.0966 |  |  | 8357877.782 |  |  | 19022009.0219 |  |  | 6820401.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 40966059.938 |  |  | Total costs |  |  |  |  | 0 |  |  | 0.1225 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2960122.4753
[5 empty] | Check pricing |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary by PAF code, breakout area
|  | 1 |  |  | ST Labor |  |  |  |  | 88462.45 |  |  | 14946 |  |  | 135019 |  |  | 191482 |  |  | 190000 |  |  | 123492 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 743401.45
|  | 2 |  |  | OT Labor |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  | 3 |  |  | Outside services - Labor |  |  |  |  | 39522.18 |  |  | 1873 |  |  | 389666 |  |  | 546151 |  |  | 6001912.0059 |  |  | 2861667.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9840792.1572
|  | 4 |  |  | Materials ( All materials incl. outside service purchased which is shown in constr. above) |  |  |  |  | 2358 |  |  | 0 |  |  | 4449911.5437 |  |  | 4678930.5387 |  |  | 4655909.2333 |  |  | 8160 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13795269.3156
|  | 5 |  |  | Removals |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  | 6 |  |  | Other |  |  |  |  | 6474.01 |  |  | 6010 |  |  | 567601.8866 |  |  | 1651577.312 |  |  | 2968843.7619 |  |  | 1525033.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6725540.3405
|  | 7 |  |  | Indirects |  |  |  |  | 209080.81 |  |  | 40387 |  |  | 754365 |  |  | 956615 |  |  | 5181507 |  |  | 2380643 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9522597.81
|  | 8 |  |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2791 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581.34
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  | 16 |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
0
[5 empty] | Total costs by PAF breakout code |  |  |  |  | 371271.79 |  |  | 66007 |  | 6524656.4303 | 5999971.4303 |  |  | 8748678.8507 |  |  | 20659072.001 |  |  | 7556496.3413 |  |  | 0 |  |  | 43926182.4133 |  |  | 43926182.4133 |  |  | 43926182.4133 |  |  | 43926182.4133 |  |  | 43926182.4133 |  |  |  |  | Total costs by PAF breakout code |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Total costs |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[9 empty] | Prior actuals to date |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  |  | 2029-01-01 |  |  | 2030-01-01 |  |  | 2031-01-01 |  |  | 2032-01-01 |  |  | 2033-01-01 |  |  | TOTAL | [9 empty] | Prior |  |  | 2024-01-01 |  |  | 2025-01-01 |  |  | 2026-01-01 |  |  | 2027-01-01 |  |  | 2028-01-01 |  |  | 2029-01-01 |  |  | 2030-01-01 |  |  | 2031-01-01 |  |  | 2032-01-01 |  |  | 2033-01-01 |  |  | TOTAL | [7 empty] | Prior |  |  | 45292 |  |  | 45658 |  |  | 46023 |  |  | 46388 |  |  | 46753 |  |  | 47119 |  |  | 47484 |  |  | 47849 |  |  | 48214 |  |  | 48580 |  |  | TOTAL
|  |  | Summary by old PAF code | [5 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
1 |  |  |  |  | Straight Time Labor |  |  |  |  | 88462.45 |  |  | 14946 |  |  | 135019 |  |  | 191482 |  |  | 190000 |  |  | 123492 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 743401.45 |  |  |  |  | Straight Time Labor |  |  |  |  | 88462.45 |  |  | 14945.95 |  |  | 128588.38 |  |  | 175350 |  |  | 168925.47 |  |  | 106595 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 682867.25 |  |  | Straight Time Labor |  |  |  |  | 0 |  |  | 0.05 |  |  | 6430.62 |  |  | 16132 |  |  | 21074.53 |  |  | 16897 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 60534.2
2 |  |  |  |  | Overtime Labor |  |  |  |  | 0 |  | ` | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Overtime Labor |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overtime Labor |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3 |  |  |  |  | Outside Services |  |  |  |  | 39522.18 |  |  | 1873 |  |  | 389666 |  |  | 546151 |  |  | 6001912.0059 |  |  | 2861667.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9840792.1572 |  |  |  |  | Outside Services |  |  |  |  | 39522.18 |  |  | 1873 |  |  | 371110.82 |  |  | 500139 |  |  | 5336171 |  |  | 2470143 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 8718959 |  |  | Outside Services |  |  |  |  | 0 |  |  | 0 |  |  | 18555.18 |  |  | 46012 |  |  | 665741.0059 |  |  | 391524.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1121833.1572
4 |  |  |  |  | Materials |  |  |  |  | 2358 |  |  | 0 |  |  | 4449911.5437 |  |  | 4678930.5387 |  |  | 4655909.2333 |  |  | 8160 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13795269.3156 |  |  |  |  | Materials |  |  |  |  | 2358 |  |  | 0 |  |  | 4320233.79 |  |  | 4453579.42 |  |  | 4343723.79 |  |  | 7044 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13126939 |  |  | Materials |  |  |  |  | 0 |  |  | 0 |  |  | 129677.7537 |  |  | 225351.1187 |  |  | 312185.4433 |  |  | 1116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 668330.3156
5 |  |  |  |  | Other – Vehicles, expenses, Contingency |  |  |  |  | 6474.01 |  |  | 6010 |  |  | 567601.8866 |  |  | 1651577.312 |  |  | 2968843.7619 |  |  | 1525033.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6725540.3405 |  |  |  |  | Other – Vehicles, expenses, Contingency |  |  |  |  | 6474.01 |  |  | 6010.3475 |  |  | 562024.8866 |  |  | 1628865.312 |  |  | 2905522.7619 |  |  | 1524188.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6633085.688 |  |  | Other – Vehicles, expenses, Contingency |  |  |  |  | 0 |  |  | -0.3475 |  |  | 5577 |  |  | 22712 |  |  | 63321 |  |  | 845 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 92454.6525
6 |  |  |  |  | Indirects |  |  |  |  | 209080.81 |  |  | 40387 |  |  | 754365 |  |  | 956615 |  |  | 5181507 |  |  | 2380643 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9522597.81 |  |  |  |  | Indirects |  |  |  |  | 209080.81 |  |  | 40386.92 |  |  | 718442.22 |  |  | 876021.05 |  |  | 4606766 |  |  | 2054931 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 8505628 |  |  | Indirects |  |  |  |  | 0 |  |  | 0.08 |  |  | 35922.78 |  |  | 80593.95 |  |  | 574741 |  |  | 325712 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1016969.81
7 |  |  |  |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2791 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581.34 |  |  |  |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2790.66 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581 |  |  | AFUDC |  |  |  |  | 0 |  |  | 0.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.34
8 |  |  |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Total costs by PAF code |  |  |  |  | 371271.79 |  |  | 66007 |  |  | 6524656.4303 |  |  | 8748678.8507 |  |  | 20659072.001 |  |  | 7556496.3413 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 43926182.4133 |  |  |  |  | Total costs by PAF code |  |  |  |  | 371271.79 |  |  | 66006.8775 |  |  | 6328493.0966 |  |  | 8357877.782 |  |  | 19022009.0219 |  |  | 6820401.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 40966059.938 |  |  | Total costs |  |  |  |  | 0 |  |  | 0.1225 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2960122.4753
|  |  |  | 0 | Check pricing |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Check pricing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Check pricing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  | 0 |  |  | 120 |  |  | 160 |  |  | 0 |  |  | 100 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 380 | [9 empty] | 0 |  |  | 0 |  |  | 120 |  |  | 160 |  |  | 0 |  |  | 100 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 380 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Summary by OLD Cover sheet code | [5 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS
| 100 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 1 |  |  |  | Construction |  |  |  |  | 10963.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5112238.0059 |  |  | 1764560.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6887762.2272 |  |  |  |  | Construction |  |  |  |  | 10963.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 4545181 |  |  | 1523138 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6079282.25 |  |  | Construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 567057.0059 |  |  | 241422.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 808479.9772
| 2 |  |  |  | Engineering / Design |  |  |  |  | 16424.06 |  | ` | 0 |  |  | 330740 |  |  | 390211 |  |  | 17431 |  |  | 34890 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 789696.06 |  |  |  |  | Engineering / Design |  |  |  |  | 16424.06 |  |  | 0 |  |  | 314989.94 |  |  | 357337 |  |  | 15498 |  |  | 30116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 734365 |  |  | Engineering / Design |  |  |  |  | 0 |  |  | 0 |  |  | 15750.06 |  |  | 32874 |  |  | 1933 |  |  | 4774 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 55331.06
| 3 |  |  |  | Land |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Land |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Land |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 4 |  |  |  | Material |  |  |  |  | 2358 |  |  | 0 |  |  | 4449911.5437 |  |  | 4678930.5387 |  |  | 4655909.2333 |  |  | 8160 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13795269.3156 |  |  |  |  | Material |  |  |  |  | 2358 |  |  | 0 |  |  | 4320233.79 |  |  | 4453579.42 |  |  | 4343723.79 |  |  | 7044 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 13126939 |  |  | Material |  |  |  |  | 0 |  |  | 0 |  |  | 129677.7537 |  |  | 225351.1187 |  |  | 312185.4433 |  |  | 1116 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 668330.3156
| 5 |  |  |  | Proj. mgmt. and supt |  |  |  |  | 104180.09 |  |  | 21783 |  |  | 311052 |  |  | 617002 |  |  | 1321608 |  |  | 439551 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2815176.09 |  |  |  |  | Proj. mgmt. and supt |  |  |  |  | 104180.09 |  |  | 21783.18 |  |  | 296239.26 |  |  | 565020 |  |  | 1175013.47 |  |  | 379413 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2541649 |  |  | Proj. mgmt. and supt |  |  |  |  | 0 |  |  | -0.18 |  |  | 14812.74 |  |  | 51982 |  |  | 146594.53 |  |  | 60138 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 273527.09
| 6 |  |  |  | removal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | removal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | removal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 7 |  |  |  | test |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 311502 |  |  | 752332 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1063834 |  |  |  |  | test |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 276950 |  |  | 649400 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 926350 |  |  | test |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 34552 |  |  | 102932 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 137484
| 8 |  |  |  | Risk / contingency |  |  |  |  | 2891.24 |  |  | 1046 |  |  | 450494.8866 |  |  | 1381997.312 |  |  | 2397976.7619 |  |  | 1518859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5753265.5705 |  |  |  |  | Risk / contingency |  |  |  |  | 2891.24 |  |  | 1046.1175 |  |  | 450494.8866 |  |  | 1381997.312 |  |  | 2397976.7619 |  |  | 1518859.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5753265.688 |  |  | Risk / contingency |  |  |  |  | 0 |  |  | -0.1175 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -0.1175
| 9 |  |  |  | escalation |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | escalation |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | escalation |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 10 |  |  |  | indirects |  |  |  |  | 209080.81 |  |  | 40387 |  |  | 754365 |  |  | 956615 |  |  | 5181507 |  |  | 2380643 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9522597.81 |  |  |  |  | indirects |  |  |  |  | 209080.81 |  |  | 40386.92 |  |  | 718442.22 |  |  | 876021.05 |  |  | 4606766 |  |  | 2054931 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 8505628 |  |  | indirects |  |  |  |  | 0 |  |  | 0.08 |  |  | 35922.78 |  |  | 80593.95 |  |  | 574741 |  |  | 325712 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1016969.81
| 11 |  |  |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2791 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581.34 |  |  |  |  | AFUDC |  |  |  |  | 25374.34 |  |  | 2790.66 |  |  | 228093 |  |  | 723923 |  |  | 1660900 |  |  | 657500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 3298581 |  |  | AFUDC |  |  |  |  | 0 |  |  | 0.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.34
| 12 |  |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Total costs by Old Cover Sheet code |  |  |  |  | 371271.79 |  |  | 66007 |  |  | 6524656.4303 |  |  | 8748678.8507 |  |  | 20659072.001 |  |  | 7556496.3413 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 43926182.4133 |  |  |  |  | Total costs by Old Cover Sheet code |  |  |  |  | 371271.79 |  |  | 66006.8775 |  |  | 6328493.0966 |  |  | 8357877.782 |  |  | 19022009.0219 |  |  | 6820401.37 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 40966059.938 |  |  | Total costs |  |  |  |  | 0 |  |  | 0.1225 |  |  | 196163.3337 |  |  | 390801.0687 |  |  | 1637062.9791 |  |  | 736094.9713 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2960122.4753
|  |  |  | 0 | Check pricing |  |  |  | 0 | 297009.64 | 0 | 0 | 57616 | 0 | 0 | 6488111.4303 | 0 | 0 | 8615076.8507 | 0 | 0 | 20254832.001 | 0 | 0 | 7175812.3413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42888458.2633 | 0 |  | 0 | 0 | Check pricing | 0 | 0 | 0 | 0 | 297009.64 | 0 | 0 | 57615.8775 | 0 | 0 | 6293688.7166 | 0 | 0 | 8235531.782 | 0 | 0 | 18662607.5519 | 0 | 0 | 6491801.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40038254.938 |  | 0 | Check pricing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1225 | 0 | 0 | 194422.7137 | 0 | 0 | 379545.0687 | 0 | 0 | 1592224.4491 | 0 | 0 | 684010.9713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850203.3253
[9 empty] | 0 |  |  | 0 |  |  | 2400 |  |  | 2680 |  |  | 240 |  |  | 460 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5780 | [9 empty] | 0 |  |  | 0 |  |  | 2400 |  |  | 2680 |  |  | 240 |  |  | 460 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 5780 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Summary by Indirect application | [5 empty] | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  |  |  | Summary by Indirect application |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  |  | Summary by WBS |  |  |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS |  | Mhrs | DOLLARS
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | GSO | Construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Eversource GSO related |  |  |  |  | 0 |  |  | 14945.95 |  |  | 95917.38 |  |  | 124934 |  |  | 149157.47 |  |  | 70384 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 527569 |  |  | Construction |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | E&S | Engineering / Design |  |  |  |  | 0 |  | ` | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Eversource E&S related |  |  |  |  | 0 |  |  | 0 |  |  | 32671 |  |  | 50416 |  |  | 19768 |  |  | 36211 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 155298.25 |  |  | Engineering / Design |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | OS | Land |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Outside services |  |  |  |  | 0 |  |  | 1873 |  |  | 371110.82 |  |  | 500139 |  |  | 5336171 |  |  | 2470143 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 8718959 |  |  | Land |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | LND | Material |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Land & Easements |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Material |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Proj. mgmt. and supt |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Proj. mgmt. and supt |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | removal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | removal |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | test |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | test |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Risk / contingency |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Risk / contingency |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | escalation |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | escalation |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | indirects |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | indirects |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | AFUDC |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | AFUDC |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Reimbursables |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | Total costs by Old Cover Sheet code |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | Summary by Indirect application |  |  |  |  | 0 |  |  | 16818.95 |  |  | 499699.2 |  |  | 675489 |  |  | 5505096.47 |  |  | 2576738 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 9401826.25 |  |  | Total costs |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | Check pricing |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Check pricing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16818.95 | 0 | 0 | 499699.2 | 0 | 0 | 675489 | 0 | 0 | 5505096.47 | 0 | 0 | 2576738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9401826.25 |  | 0 | Check pricing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Additional Est Input
Project Title: Battery Storage - Hyde Park
[5 empty] | Project Number: 21334 | [36 empty] | Estimate done by: PAG | 0
[5 empty] | WO & Task #: 80089926 | [16 empty] | Cost per LB for Steel | 2.5375 | [18 empty] | Date of Estimate:12/08/2023
[5 empty] | Estimate #: E-23-373 | [36 empty] | Estimate revision #: 00
Working Pricing Area
[5 empty] | Scope | [21 empty] | Extended Costs
|  | WBS code 1 | WBS code 2 | sum code 1 | Description | QTY | UOM | Qty (2) | UOM (2) | %'s input | Unit Mhr w/o PF | MHR PF factor | Unit Mhr w/ PF | Install By | Supply By | Labor code | Labor $/HR | Labor $ / UOM | Constr. Equipment $/hr | Constr. Eqt. / UOM | Material $ / UOM | steel wt # | Other $ / UOM | Total $ / UOM | Notes | Notes - Pricing | Total Labor hours Eversource | Total Labor hours Contractor | Total hours | Total Labor $ Eversource | Total Labor $ Contractor | Total Labor $ | Total Eversource Constr. Eqt. $ | Total Contractor Constr. Eqt. $ | Total Constr. Eqt. $ | Total Mat $ Eversource | Total Mat $ Contractor | Total Mat $ | Total Eversource other $ | Total Contractor other $ | Total other $ | TOTAL ( unescalated)
1 | 1LS |  |  | 1 | Contractor Mobilization & DeMob | 1 | LS |  |  | 5% | 0 | 1 | 0 | Other | E | EC | 152 | 256253.9 | 0 | 0 |  |  | 0 | 256253.9 | If vendor pricing bid is used that includes mob/demob, remember to remove from here | Does not include MOB/DEMOB for Contractor labor and equipment. | 0 | 0 | 0 | 0 | 256253.9 | 256253.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256253.9
2 | 59EA |  |  | 59 | BESS contract for Hyde Park PV site labor and equipment | 1 | EA |  |  |  | 27554.1863 | 1 | 27554.1863 | Other | E | EC | 152 | 4188236 | 34 | 936842 | 0 |  | 0 | 5125078 | based on pricing provided for BESS indicative pricing dated 7/28/23 | Labor and material was taken from company #3 of 5 on the indicative pricing sheet, dated 7/28/2023 | 0 | 27554.1863 | 27554.1863 | 0 | 4188236 | 4188236 | 0 | 936842 | 936842 | 0 | 0 | 0 | 0 | 0 | 0 | 5125078
3 | 59EA |  |  | 59 | Transportation and Spare Parts | 1 | EA |  |  |  |  | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 | 585677.24 |  | 0 | 585677.24 | based on pricing provided for BESS indicative pricing dated 7/28/23 | Labor and material was taken from company #3 of 5 on the indicative pricing sheet, dated 7/28/2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585677 | 0 | 585677 | 0 | 0 | 0 | 585677
4 | 59EA |  |  | 59 | Battery system and all subcomponents | 1 | EA |  |  |  | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 | 10582425.34 |  | 0 | 10582425.34 | based on pricing provided for BESS indicative pricing dated 7/28/23 | Labor and material was taken from company #3 of 5 on the indicative pricing sheet, dated 7/28/2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10582425 | 0 | 10582425 | 0 | 0 | 0 | 10582425
5 | 59EA |  |  | 59 | PCS Units | 1 | EA |  |  |  | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 | 832022.44 |  | 0 | 832022.44 | based on pricing provided for BESS indicative pricing dated 7/28/23 | Labor and material was taken from company #3 of 5 on the indicative pricing sheet, dated 7/28/2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832022 | 0 | 832022 | 0 | 0 | 0 | 832022
6 | 51EA |  |  | 51 | Step up Transformers | 1 | EA |  |  |  |  | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 | 630371.76 |  | 0 | 630371.76 | based on pricing provided for BESS indicative pricing dated 7/28/23 | Labor and material was taken from company #3 of 5 on the indicative pricing sheet, dated 7/28/2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630372 | 0 | 630372 | 0 | 0 | 0 | 630372
7 | 59EA |  |  | 59 | Communications | 1 | EA |  |  |  | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 | 466766.88 |  | 0 | 466766.88 | based on pricing provided for BESS indicative pricing dated 7/28/23 | Labor and material was taken from company #3 of 5on the indicative pricing sheet, dated 7/28/2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466767 | 0 | 466767 | 0 | 0 | 0 | 466767
8 | [5 empty] | 0 | [5 empty] | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 69LS |  |  | 69 | 2027 Rental - Spot Generation | 1 | LS |  |  |  | 683.61 | 1 | 683.61 | Other | E | EC | 152 | 103909 | 15.2 | 10391 | 0 |  | 139700 | 254000 | 2-2MW Generator locations at 33.6K ea/3 mo. Placed into other for Rental costs. Total rental costs split between labor and equipment 45/55% | mobilization is included and subtracted from MOB DEMOB Above. | 0 | 683.61 | 683.61 | 0 | 103909 | 103909 | 0 | 10391 | 10391 | 0 | 0 | 0 | 0 | 139700 | 139700 | 254000
10 | [5 empty] | 0 | [5 empty] | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | [5 empty] | 0 | [5 empty] | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | [10 empty] | 0 | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | [11 empty] | 1 | 0 | Other | E | EC | 152 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | [26 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 |  |  |  |  | TOTAL ESTIMATED COST | 1 |  | 1 | [18 empty] | 0 | 28237.7963 | 28237.7963 | 0 | 4548398.9 | 4548398.9 | 0 | 947233 | 947233 | 13097263 | 0 | 13097263 | 0 | 139700 | 139700 | 18732594.9
146
Scope Summaries
| 1ls |  |  | 1 | General mob / demob | 1 | ls | [19 empty] | 0 | 0 | 0 | 0 | 256253.9 | 256253.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256253.9
| 20 |  |  | 2 | General site work - general inc roads/paving | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3ea |  |  | 3 | foundations - Poles - direct embed | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 40 |  |  | 4 | foundations - Poles - formed conc. | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5cy |  |  | 5 | foundations - station | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6cy |  |  | 6 | foundations - buildings | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 70 |  |  | 7 | Piling / Caissons | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80 |  |  | 8 | ROW work ( clearing/ Grubbing/ access roads) | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 90 |  |  | 9 | Mats | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 100 |  |  | 10 | Crane pads | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11cy |  |  | 11 | Excavation ( incl machine / hand / trench) | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12cy |  |  | 12 | Rock Excavation | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13cy |  |  | 13 | Soil disposal | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14cy |  |  | 14 | Backfill - earth | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15cy |  |  | 15 | Backfill- stone ( incl trap rock and surfacing) | 0 | cy | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16lf |  |  | 16 | Fence / Gates | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 17lf |  |  | 17 | CIP Fence, Gates, Balistic protection | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 180 |  |  | 18 | Sound walls/ retaining walls | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 190 |  |  | 19 | Other | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 200 |  |  | 20 | Trench (Trenwa type) | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 21lf |  |  | 21 | Ductbank ( incl conduit) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22lf |  |  | 22 | Conduit - AG | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 23lf |  |  | 23 | Conduit - UG ( excl ductbank) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 24lf |  |  | 24 | Cable tray | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 25lf |  |  | 25 | Grounding | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 260 |  |  | 26 | Lighting | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 270 |  |  | 27 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 280 |  |  | 28 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 290 |  |  | 29 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 30lf |  |  | 30 | Cable - UG - HPFF ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 31lf |  |  | 31 | Cable - UG - XLPE ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 32lf |  |  | 32 | Cable - AG under 115kv ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 33lf |  |  | 33 | Cable - AG 115 kv ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 34lf |  |  | 34 | Cable - AG 345 kv ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 35lf |  |  | 35 | Cable - OPGW / Shield ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 36lf |  |  | 36 | Cable - Control ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 37lf |  |  | 37 | Cable - Communication / Oher ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 38lf |  |  | 38 | Cable - Power ( incl terms) | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 39lf |  |  | 39 | Cable - Other | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400 |  |  | 40 | Structures - buildings | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 41ea |  |  | 41 | Structures - Poles - monopoles | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 42ea |  |  | 42 | Structures - Poles - frame | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 43ea |  |  | 43 | Structures - Poles - Guys | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 440 |  |  | 44 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 45tn |  |  | 45 | Structures - S.S. | 0 | tn | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 46tn |  |  | 46 | Structures - Platforms | 0 | tn | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 470 |  |  | 47 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 480 |  |  | 48 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 49tn |  |  | 49 | Structures - Others | 0 | tn | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 50ea |  |  | 50 | Major Eqt - Circuit Breakers | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 51ea |  |  | 51 | Major Eqt - Transformers | 1 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630372 | 0 | 630372 | 0 | 0 | 0 | 630372
| 52ea |  |  | 52 | Major Eqt - Circuit Switchers | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 53ea |  |  | 53 | Major Eqt - Disconect Switches | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 54ea |  |  | 54 | Major Eqt - Cap Banks | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 55ea |  |  | 55 | Major Eqt - Reactors | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 56ea |  |  | 56 | Major Eqt - GIS | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 57ea |  |  | 57 | Major Eqt - Switchgear | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 580 |  |  | 58 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 59ea |  |  | 59 | Major Eqt - Other | 5 | ea | [19 empty] | 0 | 27554.1863 | 27554.1863 | 0 | 4188236 | 4188236 | 0 | 936842 | 936842 | 12466891 | 0 | 12466891 | 0 | 0 | 0 | 17591969
| 600 |  |  | 60 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 610 |  |  | 61 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 620 |  |  | 62 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 63lf |  |  | 63 | Misc. Eqt - Bus | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 64lf |  |  | 64 | Misc. Eqt - Conduit / Tray | 0 | lf | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 65ea |  |  | 65 | Misc. Eqt - Insulators | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66ea |  |  | 66 | Misc. Eqt - LA's | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 67ea |  |  | 67 | Misc. Eqt - CCVT | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 680 |  |  | 68 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 69ea |  |  | 69 | Misc. Eqt - Other | 0 | ea | [19 empty] | 0 | 683.61 | 683.61 | 0 | 103909 | 103909 | 0 | 10391 | 10391 | 0 | 0 | 0 | 0 | 139700 | 139700 | 254000
| 700 |  |  | 70 | Control house Buidling | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 710 |  |  | 71 | Pre-Eng Building | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 720 |  |  | 72 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 730 |  |  | 73 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 740 |  |  | 74 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 750 |  |  | 75 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 760 |  |  | 76 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 770 |  |  | 77 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 780 |  |  | 78 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 790 |  |  | 79 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 800 |  |  | 80 | Protection and Controls | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 81ea |  |  | 81 | Relays | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 82ea |  |  | 82 | Cabinets | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 83ea |  |  | 83 | Comm. Eqt | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 84ea |  |  | 84 | SCADA | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 85ea |  |  | 85 | Batteries | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 860 |  |  | 86 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 870 |  |  | 87 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 880 |  |  | 88 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 89ea |  |  | 89 | Misc. Protection and controls Eqt. | 0 | ea | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 900 |  |  | 90 | Environmental | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 910 |  |  | 91 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 920 |  |  | 92 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 930 |  |  | 93 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 940 |  |  | 94 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 950 |  |  | 95 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 960 |  |  | 96 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 970 |  |  | 97 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 980 |  |  | 98 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 990 |  |  | 99 | REMOVALS | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | Uncoded amounts ( fix the coding before continuing) |  | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Totals | [21 empty] | 0 | 28237.7963 | 28237.7963 | 0 | 4548398.9 | 4548398.9 | 0 | 947233 | 947233 | 13097263 | 0 | 13097263 | 0 | 139700 | 139700 | 18732594.9 | check total